## Template for institutions
cxxxxxxxx |  | HREiR Action plan template 2022-2024
|  | Institution name: | SOAS University of London |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
|  | Cohort number: | Cohort 5 |  |  |  | Audience (beneficiaries of the action plan) |  |  | Comments
|  | Date of submission: | 29/07/2022 update on progress submitted 20/09/24 |  |  |  | Research staff | Number of | 50 | Those on a research-only contract
|  | Institutional context: | A global university in the heart of London’s vibrant university quarter, SOAS University of London spans the arts, humanities and social sciences. Our expertise is uniquely rooted in the political, social, economic, historical and cultural dynamics of Africa, Asia, the Middle East and their diasporas. SOAS is a relatively small institution with approximately 50 research-only staff, 235 research and teaching staff, 90 teaching-only staff, and 30 professional services staff with a research remit role. With 410 PGR students, we have a higher proportion of research students to undergraduates than most UK higher education institutions. SOAS celebrates diversity. We have an ethnically more diverse workforce than other UK institutions: 41% of academic staff, 43% of non-academic staff, and 58% of our students are from Black and Minority Ethnic groups. While the numbers mean that SOAS has surpassed sector averages, we want to look beyond that. We know that we experience the world and institutions based on how we are positioned along race, gender, and class. We are therefore bold and decisive in our resolve to name these inequalities at SOAS and dedicate resources to resolving them during the strategic plan period 2021-2026. |  |  |  | Postgraduate researchers | 50 | 410 | MPhil and PhD students
[7 empty] | Research and teaching staff | 410 | 235 | Academic staff on teaching and research (T&R) contracts
[7 empty] | Teaching-only staff | 235 | 90 | Staff on Academic Education-Focused Route (AER)
[7 empty] | Professional support staff | 90 | 30 | Staff whose roles directly support research
30
| Complete for submission | [7 empty] | To be completed only when reporting on action plan
|  | Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
| ECI1 | Ensure all relevant staff are aware of the Concordat. | 1. Develop a communication strategy to inform all relevant stakeholders about the Concordat and include link to the Concordat in the PRP template and Staff Development webpage 2. Review institutional templates for Research and HR and make sure that a Concordat link is added 3. Recruitment team invite all new staff to HR Induction where the Concordat will be shared and promoted 4. L&D team signpost to relevant information during induction and via New Staff newsletter | 1. carried over 2. not carried over 3. not carried over 4. not carried over | Recruitment team to produce termly report on number of employees in research based roles who attend inductions starting T1, 2022/23 (30/11/22). Final report with a comparatives of attendance will be produced in June-2024 (30/06/24). Comms Strategy to launch by 30 November 2022 to coincide with the institutional staff survey All-staff survey to take place by T2 2022/23 (31 December 2022) and at least twice a year surveys for all staff (a mixture of pulse and full) ongoing. | 1,2,3 and 4: Recruitment team & L&D team & HR Director | In first year, in response to the published HR communication strategy 40% of responding Staff rate HR communication as effective or very effective (Annual staff survey). 60% of responding staff indicate awareness of the Concordat. 80% of new staff attend the HR Induction and are made aware of the Concordat; 100% of L&D Newsletters includes reference to Concordat . |  | 1. Completed: Due to redundancies in 2021 the priorities of HR changed and as such a question relating to the awareness of the concordat was not raised in the All Staff Survey in 2022, therefore there is no data on staff awareness of the concordat. However, we are able to verify the completion of the action through the communication strategies HREiR and the Concordat are now effectively communicated through HR's communications strategy. Link is include in PRP template and staff development intranet pages and website. 2. Completed: HREiR and the Concordat are now effectively communicated through HR's communications strategy. Both awards have been added to template JDs which all staff use to recruit new posts. Where relevant the awards are also in the copy of the job ad on the website, jobs.ac.uk and any other ads. 3. Completed: The link is include in PRP template and on the staff development intranet pages and website. The new starter induction delivered by HR (held monthly) includes slides on the Concordat and HREiR and the teams which deliver this. 100% of new starters are thus informed about these. 4. Completed: All relevant links to the Concordat are included in the induction, and in the new staff newsletter. | The entire staff population of 1,110 uses the Intranet to find information. 100% of staff have access to the information through channels, including the induction newsletter. The Concordat link has been added to the SDR institutional template but needs to be further embedded in other relevant institutional templates for the future. 24 inductions have been held monthly since the last reporting period. Since 2022, SOAS has had 56 new joiners out of a population of 1,100 total staff. It is mandatory for all new starters to attend the induction and is monitored through probation review. | No further action
| ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | 1. Develop Staff online handbook including information on relevant policies and procedures (HR Management Team) 2. Improve the management of HR data and the information on researcher appointments to aide monitoring 3. At least two researchers to sit on relevant committees, including Athena Swan and the Race Equality Charter WGs, but also be part of wider consultations regarding new and updated policies | not carried over | 1. 01/06/2023 2. T3 2023 (30/06/23) 3. Approved by BoT by end of November 2022 | 1,2 Deputy Director - Policy and Reward 3. Director of Governance | 1. 100% of new and existing staff receive the online handbook. 2. Regular reporting on SOAS staff covered by the Concordat is in place - monitored by the Research Culture Sub-Committee 3. As the institution moves to new College structure terms of reference and committee membership include at least two researchers |  | 1. Completed: The managers handbook was launched in April 2023 and includes all relevant policies and processes, and other helpful information. All managers receive this. All policies are on the intranet and where relevant the website. 2. Completed: HR BP regularly updates the Research Culture team on appointments. New working group established with Academic Heads of Department to inform Research Culture team of new appointments as well. 3. Completed: Researchers have been included in the Terms of Reference for these committees and WGs since September 2022 | Launched in April 2023. 500 staff of a population of 1,110 are managers and have received the handbook. Easier communication with ECRs that come into departments. Over the two years the cohort of 100 ECRs have had regular communication from the Research Culture team via a newsletter and regular catchups. | No further action
| ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | 1. Analysis of the all-staff survey regarding questions on wellbeing, workload, and levels of satisfaction with institutional offerings related to wellbeing. Surveying staff, including staff on research contracts, regarding their wellbeing on an annual basis. Analysis of the survey data in relation to the Concordat principles will be reported on an annual basis to the Research Culture Sub-Committee 2. Embed reporting on quality of research culture in new governance structures [committee terms of reference and roles] 3. Conduct and analyse Postgraduate Research Experience Survey (PRES) on a biannual basis. | not carried over | 1.T2 2023 30/04/23 2. Signed of by BoT by 30 November 2022 3. 31 March 2023 | 1. Director of HR & Pro-Director Research and Knowledge Exchange 2. Director of Governance 3. Head of DS | 1. Recommendation paper submitted to the summer 2023 Research Culture Sub-Committee. 2. Terms of reference signed off with reporting on the quality of the research culture embedded in the new governance structure 3. Increase the PGR student satisfaction rate to 80% in the March 2023 PRES survey. |  | 1. Completed: An all staff survey was conducted in 2022. Analysis of the all-staff survey revealed that well-being and workload have been major issues so these are areas of focus for the future. Feedback and data from our research culture focus groups. In total, 556 out of 1062 members of staff responded to the survey – which is a 52% response rate. 83% of respondents said they understood how their work supports SOAS' objectives. Nearly half of respondents (47.1%) consider their physical /mental health worse than before the pandemic. 45.5% of survey respondents do not feel their workload is manageable, and one third feel they cannot take their full annual leave allowance. A quarter of staff can easily find wellbeing information and guidance at SOAS and would know where to sign post a colleague with guidance on a well-being topic. 2. Completed: All committees have a robust Terms of reference, clearly defining roles and responsibilities. 3. PRES survey 2023 undertaken and results analysed. | 1. In March 2024 the Culture team conducted in-depth focus groups with researchers at different career stages. In attendance were 15 ECRs and 15 mid-career researchers at two sessions. Using these methods of feedback the Culture team now is embedded in HR survey practices with developed working relationships so that that the needed data can be gathered from staff surveys to avoid having to repeat data gathering. 2. There is now formal reporting of research culture in the new governance structures, with a Research Culture Committee (launched in January 2023) that reports into the SOAS Research and Knowledge Exchange Committee, which itself reports to Senate, which is accountable to the Board of Trustees. 3. The PRES 2023 results did not achieve an 80% satisfaction rate and overall made for sobering reading. A great deal of the problems seem to stem from instability in staffing in our Doctoral School. However, a new Head of the Doctoral School was recruited and began work in Sep 2023, and with the new Doctoral School Manager and team has created a robust PRES action plan during 23/24 to improve PGR support in all the areas that did not do well in the PRES 2023 survey. | 1. No further action 2. No further action 3. Ongoing
| ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Annual meeting with HoDs to reinforce the importance of more experienced researchers mentoring newer researchers and to regularly attend the ECR Forum. Report every 6 months by department to monitor progress on mentoring matches | carried over | annually 30 September | L&D BP; Recruitment and workforce Reporting Manager; Director of HR; HoDs, Department Research and KE Convenors | Termly emails reminding researchers of training related to mentoring and that they are expected to take part in this. 50% of ECRs attend ECR Forum and 100% of ECRs are included in academic departmental activities, such as research seminars. |  | Complete: Take up, engagement, and evaluation of our new SOAS-wide research mentoring framework, in which we have encouraged senior researchers to mentor more junior researchers. Engagement by ECRs, their line managers, and HoDs with our research culture activities. | A new SOAS-wide research mentoring framework was initiated by the Deputy Dean for Research Culture in 2022/2023 and, with the mandate of the Board of Trustees, rolled out in the 2023/2024 year. In July 2024 a survey was conducted on this mentoring programme to evaluate practices for the next round. Out of a population of 86 colleagues on the programme (49 mentees and 37 mentors) we had a response rate of 39% for mentors and 30% for mentees. Some of the positive feedback is as follows: one mentee said "I come away from mentor meetings with a renewed impetus to make time for research, and some enthusiasm to do so." One mentor said: "I have absolutely loved being a mentor and feel that I learned as much from my two mentees as I hope they learned from me." In addition to this, the culture team regularly meets with HoDs to provide updates and gather feedback, and also runs regular meetings with a range of ECRs, including a start-of-year and end-of-year social and information event for ECRs and their line managers which we initiated in this 2022-2024 period. Attendance at the start-of-year events has been particularly good, and these are attended by our DVC for RKE to show ECRs how much we value them in the institution. | No further action
Wellbeing and mental health ***
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
| ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | 1. A series of 12 training sessions will continue to be offered as part of the Managers Development Programme 2. Launch of Managers Handbook in Term 3, 2021/22 3. Full implementation of the workload allocation model (WAM) | 1. Carried over - but a new system 'Inkpath' has been implemented, which provides the ability to measure attendance and satisfaction ratings. 2. Carried over 3. Carried over | 1. End of each academic year 31 July 2. 30 September 2023 3. WAM fully implemented in 2022/23 (date tbc) | HRBP | 1. Measure attendance by comparing list of current managers for research staff against training completions. 60% attendance of the relevant staff and of course attendees a 60% satisfaction rating for the workshops; this will be measured and reported on annually (31 August each year), with oversight/review at the next Research Culture Sub-Committee meeting. 2. 100% of new and existing managers at SOAS will be given the handbook. 3. 100% of research staff manage their workload through WAMS. |  | 1. Completed: Since 2022, 12 sessions per year have taken place on a range of subjects, including stress management, mental health in the workplace for managers, menopause in the workplace, and many more. 2. Completed: This was completed and widely shared in 2023 and includes information on HREiR and related Concordats, mental health and well-being resources and much more. 100% of managers receive this handbook. 3. Completed: Since March 2024, HoDs have started to be able to fully use the WAMS. Working with the Culture team, EDI and those working across Athena Swan, the WAMS now reflects and incorporates many activities previously 'unseen' which can adversely fall to certain groups to carry out. | 1. Responding to the 2022 all staff survey data which indicated respondents feel workload is not manageable, these sessions helped to support staff. Plans for new staff survey including wellbeing questions are in progress for academic year 24/25 2. There is a document managers can now turn to for information and we have reminded line managers of this in our HREiR meetings with them. 3. The WAMS has provided far more clarity on who is doing what, what WAMS tariffs there are for different activities and responsibilities, and this should lead to more parity between staff. 100% of academic staff (556 people) at SOAS utilise the WAMS. | No further action
| ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | 1. Wellbeing for Managers workshop will continue to be offered termly; further offerings continue to be available on LinkedIn Learning 2. REACT training will be rolled out to enable managers to support staff in having wellbeing conversations as of Term 2, 2022/23 | Managers training is a carried over action; REACT training is a new initiative | REACT Training rollout deadline: 31 March 2023 | Staff Wellbeing Lead | 1. & 2. 30% more managers confirm that they have attended the wellbeing workshops and indicate in feedback that they feel more comfortable having wellbeing conversations with their research staff. |  | 1. Completed: Wellbeing training has been offered through the overall Managers training. In addition, in 2023 the Employee Assistance Programme (EAP) was launched, offering a wealth of resources from counselling, videos and PDFs on a range of topics related to physical and mental health and well-being. LinkedIn Learning is also utilised within the School to support wellbeing offer. 2. Delayed: Implementing REACT training was delayed due to resourcing issues. Two sessions have been confirmed for 2024 - 7th July 2024 and 20th September 2024. These were advertised in the all staff bulletin and on training platforms, and was also presented to HoDs and line managers at 1 May 2024 meeting. | 1. Increased wellbeing support for researchers and managers of researchers. Since its launch on 31 July 2023 there have been 52 enquiries made through the platform, of which 70% were related to mental health. 21% of those interacting with the platform are male, while 18% were female and 12 identified as other /non-binary. | 1. No further action 2. Ongoing
| ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health. | Staff Wellbeing Lead to contact all managers to advise them to encourage their direct reports including researchers to attend activities such as Wellbeing Fortnight offerings and other wellbeing events, and undertake training for themselves to understand how they can support their direct reports | not carried over | Termly 31 December, 30 April and 31 August | Staff Wellbeing Lead | Activities promoted in Staff Bulletin, via the Managers email list; and via the researcher email list resulting in a 30% increase in attendance at wellbeing events resulting in 50% of research staff respondents to the all staff and wellbeing surveys stating that genuine and effective steps are being taken to support their wellbeing. |  | Complete: Managers HR Briefing programme launched in Jan 24 and takes place monthly. Wellbeing slides are included in these induction sessions. | The emails and meetings raising the profile of these activities has increased awareness amongst the staff population. 100% of new line managers attend these inductions at appointment. These updates are included in the weekly all staff bulletin (email) to ensure 100% of staff are informed. | No further action
| ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | HRMT to include information on flexible working in Managers' Handbook and Staff Handbook and in the Communications Strategy | not carried over | Managers handbook to be sent to all managers by end of T3 - 31/07/22. Staff Handbook to be sent to all staff by end of T1 -31/12/22 | Director of HR; HRMT | 50% of surveyed staff (all staff survey)said they were aware of flexible working policy. All staff have received information relating to flexible working. |  | Complete: Flexible working is promoted through HR's communications strategy in a variety of ways, such as inductions, the staff handbook and staff intranet. Processes and policies are widely accessible. An all staff survey was conducted in 2022. balance. | A majority of staff are satisfied with flexible working hours and arrangements offered at SOAS. In the future we will review why some feel they cannot maintain a good work/life balance. In the 2022 survey 556 out of 1062 members of staff responded to the survey – which is a 52% response rate. 70% of respondents said they were satisfied with the flexibility of their hours. However, only 46% of respondents said they were able to achieve a good life/work balance. | No further action
| ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health. | 1. Staff Wellbeing Lead to email researchers each term to encourage them to attend Wellbeing-related activities, such as Mental Health Awareness, Yoga, Wellbeing Fortnight, etc. 2. All researchers are signposted to the Wellbeing page and encouraged to complete Wellness Action Plan in these emails each term and to attend the annual Wellbeing Festival. 3.Real time staff wellbeing pulse survey conducted 2 times per year will provide an improvement of 50% of respondents to the survey stating that genuine and effective steps are being taken to support their wellbeing. | not carried over | Termly 31 December, 30 April and 31 August | Staff Wellbeing Lead | 1. Emails sent to researchers at least once per term, and complete a wellness action plan to ensure at least 5% take up. 2. Report on improvements implemented and supported by the School's wellbeing strategy. Employee Assistance Programme will be regularly reviewed with the service providers and reported to the Health, Safety and Security Committee. 3. The wellbeing festival success will be measured through percentage of offerings booked, number of attendees and positive feedback through a focus group. |  | 1. Complete: Wellbeing activities are publicised in the all-staff bulletin and colleagues are encouraged to attend. Via Spectrum Life’s EAP and Wellbeing Digital Platform researchers can access wellbeing content and training created and curated by leading industry experts, from support with mental health to ﬁtness videos, nutrition plans and recipes etc. The digital platform gives staff access to support at any time and content on over 5,000 health and wellbeing seminars and self-learning across 250 topics. All the Health and Wellbeing events are available via Video link and the Spectrum.Life App with clinically approved mental health content and e-learning, counselling and psychotherapy sessions. Staff also have access to a digital gym (with live classes), topical wellbeing series and bespoke events delivered by experts and guest presenters from Spectrum’s digital wellbeing studio. 2. Completed: The wellbeing page and Employee Assistance Programme is sent to all staff via the all staff bulletin weekly. All activities are advertised here. 3. Not delivered: Due to resource issues in the wellbeing team, this action was delayed and will be carried over to the forward-looking action plan for 2024-2027. The culture team are working to ensure ECRs and academics are at the heart of this work on improving wellbeing. | In 2024, the bi-annual all staff survey will indicate the success of these new measures. Line managers of ECRs inform the culture team that they and the employees they manage feel better supported through the Employee Assistance Programme. | 1. No further action 2. No further action 3. Carried over
Bullying and harassment ***
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents.
| ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | Publicise the 24-hr Employee Assistance Programme support to Research Staff at induction and in handbook. Short-term publicise to Research Staff in staff communications Improved procedures for reporting complaints as well as increased awareness in managers. | not carried over | Managers handbook, with details of the employee assistance programme, to be sent to all managers by end of T3, 2021/22 31/07/22. Staff Handbook to be sent to all staff by end of T1, 2022/23 31/12/22. All staff emails to be sent re flexible working and EAP by 31st August 2022 Comms and Dignity at SOAS policy, new Grievance and Disciplinary policies shared with 100% research staff. The options for reporting incidents of bullying and harassment are being reviewed with refreshed comms by 31 October 22. The improved policies and guidance raise awareness of research staff and their managers. | Deputy HR Director - Policy & Reward | 100% of staff have received information relating to EAP support available to all staff and we record up to 5% average use of the service. Mandatory training exists on EDI issues related to bullying and harassment and discrimination. 80% of managers of research staff are offered bullying and harassment training. |  | Complete: 100% of all staff receive information about the Employee Assistance Programme via the all-staff bulletin, staff intranet and inductions with HR and line managers. All staff are offered information and training on bullying and harassment. | Staff are better informed about the support offered at SOAS in relation to bullying and harassment. Since its launch in July 2023, there have been 52 recorded users of the EAP site, out of a staff population of 1,110 (5%). | No further action
| ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment. | Continue to offer training to all managers on handling grievance and disciplinary issues including discrimination, bullying and harassment. Additionally, guidance and support from HR Business Partners to Managers on individual or team issues. | not carried over | Termly by 31 December, 30 April and 31 August | L&D BP; Deputy HR Director - Policy & Reward | Measured by number of managers who attend HR Managers Briefing training on Grievances. 60% of participants record that they know more and are confident about the process. |  | Complete: The training programme offered by HR developed to include sessions on discrimination and harassment in the mandatory training package, which all staff have to complete in order to pass probation. | Staff have in place a robust training programme on the systems and policies for grievance, bullying, and discrimination. Staff are better informed about practices through the handbook and intranet. While a system for the recording attendance and undertaking of training is in place an issue has been identified with the platform which has led to inconsistent and inaccurate data collection. This is an issue that is actively being worked on to ensure accurate data can be collected in the future. | Ongoing
| ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying. | Review numbers of employee relations cases and use annual HR survey to survey Research Staff on whether cases are reported | not carried over | Starting term 1, 2022/23 31/12/22; then reviewed termly 30 April and 31 August | Deputy HR Director - Policy & Reward | Measured by comparing numbers of ER cases against survey data - 40% in year 1, 50% in year 2 of respondents who report experiencing discrimination, bullying and harassment formally report it |  | Experienced issues: Issue identified with the way employee relation cases were being recorded at organisation. HR have reviewed the issues and are developing more robust and accurate methods to record and report to the appropriate governance structures, integrating the needs of HREiR. | Accurate data not available for the period. Enhanced data collection and reporting routes have been developed going forward. | Ongoing
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
| ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | Unconscious Bias, Equality & Diversity Overview continue to be mandatory for all staff | carried over | Unconscious Bias training by 30 June 2023 | EDI team; Deputy HR Director - Policy and Reward; Director of HR | 100% of managers to have undertaken Unconscious Bias training. Data to be reported termly to the EDI Committee |  | Complete: Unconscious bias and EDI are a continued part of the mandatory training, which is a requirement to pass probation. As well as this, SOAS has policies and practices on the staff intranet for all to access. These policies are also foregrounded in the induction process. | The training and policies in place ensures these are embedded in the organisational structure and promotes EDI amongst teams. While a system for the recording attendance and undertaking of training is in place an issue has been identified with the platform which has led to inconsistent and inaccurate data collection. This is an issue that is actively being worked on to ensure accurate data can be collected in the future. | No further action
| ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | Unconscious Bias, Equality & Diversity Overview continue to be mandatory for all staff. Within induction SOAS policies are shared.(NB SOAS Policies are shared and Funder Policies are shared by Line Manager to research staff) | carried over | Unconscious Bias training by 30 June 2023 | HR Directorate & EDI team , Line Manager/PI | Scores in research staff survey evidence a positive (75%+) score on questions asking about awareness of employer and funder policies related to Equality Diversity and Inclusion. |  | Experienced issues: Unconscious bias and EDI are a continued part of the mandatory training, which is a requirement to pass probation. As well as this, SOAS has policies and practices on the staff intranet for all to access. These policies are also foregrounded in the induction process. A research-focused survey was not undertaken in this period but is prioritised in our forward-looking action plan for 2024-2027. | Since we did not undertake a research-focused survey during this period we cannot report on this particular point in terms of impact. However, SOAS's activities in this area have been wide ranging and impactful, as discussed in the overview report. For example The BMEntoring external mentoring programme launched in 2023 and allows staff members from minoritised backgrounds at SOAS to be paired with an external mentor or to be a mentor. During 2023-2024 there were 10 mentees and 6 mentors. The black staff management programme which launched in 2023-2024 had a total of 12 SOAS staff involved. | Carried over
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity, and are able to report infringements or misconduct.
| ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | 1. Continue the subscription to Epigeum Research Integrity course and promote uptake of the mandatory Epigeum Research Integrity 2.0 course among researchers and their managers. 2. Set up a PhD supervisors research ethics training. | 1. carried over 2. not carried over | 1. Ongoing 2. 31 Jan 2023 | Research Ethics & Governance Officer | 1. 30% increase in the number passing the online research integrity course in two years. Monitored and reported annually to REC and the Board of Trustees in May, in the form of a research integrity statement. 2. The PhD supervisors' research ethics training course is set up and well received via feedback questionnaire |  | 1. Complete: Research integrity statement (public, on the website); REP report to RKE committee. 2. Delayed: Due to change in priorities this course was not launched in 2023. The Ethics and Integrity Office is working with Doctoral School to launch within the next 12 months | 1. 72% of staff pass Research Integrity. Once someone has passed the Epigeum test, that counts for 3 years. Ongoing (Epigeum Research Integrity 2.2 course launching June 2024 so new data will start being gathered then for next 3 years) | 1. Ongoing 2. Complete
| ECM3 | Ensure managers' report and address incidents of poor research integrity. | 1. Raise awareness at the Research and Knowledge Exchange Committee, with each HoD and during Managers training on the SOAS Policy Investigating Allegations of Research Misconduct. 2. Confirmation of quarterly updates sent via the research bulletin; data forming part of the annual RIAS report; updates circa 2022 (feeding into next academic year) highlighted via both the Research Ethics Panel (REP) and Research and Enterprise Committee (REC) | not carried over | 31 Oct.2022 | Research Ethics & Governance Officer | 1. & 2. 60% of managers indicate in annual staff survey that they feel comfortable with the level of research standards, integrity and misconduct reporting processes in the next 2 years |  | 1. Complete: Our research misconduct statement is on the website and shared through multiple routes to HoDs and managers. The number of cases is reported annually to BoT. 2. Complete: Appointment of the new Chair to the Research Ethics Panel (REP) has recently taken effect (Jan-2024) for a 3-yr tenure. The research bulletin (which goes to all staff with research in their contract) includes updates on research integrity. There is also a new termly research ethics bulletin that was launched at the end of 23/24 by the Chair. The bulletin covers changes that are and/or have occurred to the research ethics and integrity framework, as well as highlighting ongoing areas of work for the Panel. Recent guidance amendments have taken place for the Research DPIA, assisted fieldwork guidance, and a new Panel guidance note on the use of AI/AGI platforms in research. The last Research Integrity Annual Statement (RIAS) was approved by the Board of Trustees in Oct-2023 and has been uploaded to the external website. | 1. The policy has been shared, however, an evaluation of managers' comfort with the process was not included in the last all staff survey. The culture team will seek feedback via survey or other method in 2024-2027 period. 2. Staff are aware of processes surrounding research integrity and all staff with responsibility for research receive regular updates | No further action
| ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity. | 1. Increase signposting via DSMG, messages sent via Research Bulletin, and drop-ins, to the Epigeum Research Integrity 2.0 course and the online Safeguarding course and refresh every three years. 2. Confirmation of quarterly updates sent via the Research Bulletin; data forming part of the annual RIAS report; updates circa 2022 (feeding into next academic year) highlighted via both the REP/REC | carried over | Ongoing reviewed Termly 31 December, 30 April and 31 August | Research Ethics & Governance Officer | 1 and 2. Any doctoral researcher and researcher with an externally funded grant completes and passes the Epigeum Research Integrity course. 100% of researchers who receive safeguarding referral complete and pass the online Safeguarding course within the required time limit. Completions reported annually to REC |  | 1. Completed: Data from PhD Manager shows that each doctoral researcher completes and uploads a copy of the completed certificate demonstrating passing the course at the Upgrade stage. We have been unable to eliminate the ‘lag-time’ for doctoral researchers between registration and passing of the Epigeum Research Integrity course. Some doctoral researchers will register for the course in year one, but only complete and pass the course in year two at the Upgrade stage. This lag-time has been formally raised with Epigeum (Sept-23, Jan-24). It is not possible to eliminate this completely from the captured data. Researchers at all levels who undertake proposed research activity with potentially vulnerable participants are mandated to complete the Safeguarding training. This is ensured at the ethics approval stage. Where required, a relevant DBS check is either held by the researcher (often at PhD level), but is also facilitated during the ethics process. Reporting for this is included in the annual RIAS. 2. Complete: reporting of outcomes included in relevant places | 1. PGRs act in accordance with policies related to research integrity - 94% (365 / 387) of PGRs passed the Epigeum Research Integrity course.
| ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | 1. Review relevant policies and procedures, i.e. the School's Research Ethics Policy and the SOAS Policy Investigating Allegations of Research Misconduct to ensure that expectations are set around academic integrity and research ethics. 2. Raise awareness of these policies and procedures to ensure that researchers report cases of research misconduct | not carried over | by 31 Oct 2022 | Head of Governance & RKED | 1 and 2. Allegations of misconduct policy to be reiterated in comms' outlining changes / updated guidance as per Sept/Oct-2022. Certain documentation will go forward to the REP/REC autumn sessions, thereafter to College and Department level Research and Knowledge Exchange Committees. |  | 1. Complete: The Research Misconduct Policy is in line with sector guidance and it is publicly available and we report on the status of all allegations (and their progression) within the annual Research Integrity Annual Statement (RIAS). Our new Bulletin on Research Ethics emphasises this. 2. Complete: There are regular updates in bulletins - standing item on funding Opps about FCDO misconduct. Annual report prepared and approved by Board of Trustees in line with concordat requirement | Greater understanding of the policies and practices, development of new policies targeted at building a robust research policy. | No further action
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution.
| EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | Two elected representatives from the academic community, one of which should be an early career researcher (an individual who is either: within eight years of their PhD award, or equivalent professional training) and one doctoral researcher nominated by the Research Students’ Association (RSA) sit on School-wide committees, including College level Research and Knowledge Exchange Committees. | not carried over | by Term 3, 2022/23 31/07/23 | Deputy Director - Policy and Reward | Two elected research representatives on School-wide committees with a remit for research and knowledge exchange. |  | Complete: Terms of Reference for committees, approved by EB, includes this in the policy. The Research Culture Committee, Research Ethics Committee, and Knowledge Exchange Committee each include 3 ECRs (one from each College) and a PhD student representative. Each College RKE committee includes an ECR representative and a PhD student rep. | Greater representation ensures research is integral to key strategic policy change and implementation. | No further action
| ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | Managers of research staff and research staff engage in research groups and committees (including at E17). Staff invited to sit on focus groups when policies are being revised. This practice will be overseen and encouraged by a new Research Culture Sub-Committee which will be established in autumn 2022. The Research Culture Sub-Committee's purpose is to share best practice and to ensure SOAS’s research environment is supportive and inclusive. | not carried over | ongoing - as policies come up for review | Deputy Director - Policy and Reward | All staff invited to sit on focus groups when opportunity arises to ensure at least 1 research staff is on the group. |  | Complete: As above. Committees also include mid-career and senior representatives so that the full range of career development is represented and so that managers of researchers can feed in to policy change and development. | Greater representation ensures research is integral to key strategic policy change and implementation. | No further action
| EM5 | Engage with opportunities to contribute to relevant policy development within their institution. | See E17 and ECM5 above | carried over | ongoing - as policies come up for review | Deputy Director - Policy and Reward | as E17 and ECM5 |  | As above. | Greater representation ensures research is integral to key strategic policy change and implementation. Will be measured through research-focused surveys during 2024-2027. | No further action
[5 empty] | by T2 2023/24 30/04/24 | Director of HR | 60% of research staff survey respondents agreed that they had/would consider opportunities to contribute to policy development.
| ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | As ECM5 | carried over | ongoing - as relevant policies come up for review | Deputy Director - Policy and Reward | as ECM5 |  | As above. | Greater representation ensures research is integral to key strategic policy change and implementation. | No further action
[5 empty] | by T2 2023/24 30/04/24 | Director of HR / HRMT | 60% of research staff survey respondents agree that they had/would consider opportunities to contribute to policy development
| ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community. | As ECM5 and EI7 | not carried over | by T2 2023/24 30/04/24 | Director of HR / HRMT & Pro-director of Research & Knowledge Exchange | 60% of research staff survey respondents agreed that they recognised themselves as key stakeholders in SOAS as ECM5 and EI7 |  | As above. | In the 2022 all-staff survey, 70% of staff respondents (500 staff) said they understood how their role supports the strategic aims of SOAS. We aim to measure this for research staff specifically through the 2024-27 period. | Ongoing
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation.
| EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | Recruitment advertising for research posts for 1+ years (not including named researchers) are completed using the e-recruitment system and are published on the internal and external job advert pages. PIs and HoDs continue to be supported by recruitment advisers throughout the process, who also provide guidance notes. Advisers continue to receive and review interview forms as part of the offer process to ensure fair selection processes have been followed. Inclusive Recruitment initiatives have been introduced to SOAS which support the achievement of EI1. Number of posts recruited following open process monitored and regularly reviewed termly. To reinforce our position further we will sign the San Francisco Declaration on Research Assessment, which commits the institution to be explicit about the criteria used to reach hiring and promotion decisions, clearly highlighting, especially for early-stage investigators, that the scientific content of a paper is much more important than publication metrics or the identity of the journal in which it was published. | not carried over | ongoing 1. starts T2 22/23 31/01/23 | Research Culture Manager (DORA actions) Recruitment & Workforce Reporting Manager | 1. By autumn 2022 to have signed up to DORA, ensure the objectives of DORA are monitored by specific reference to them in the terms of reference for the Research Culture Sub-Committee and to have launched an internal communication plan relating to DORA. 2. Termly reports on recruitment produced with figures 3. 80% of researchers (not including named researchers) on 1+ year contracts recruited through an open process |  | Some delays: While we have signed up to DORA and are actively monitoring it as part of the ToR for the Research Culture Committee, a full communication plan around it was not launched and more needs to be done on this front in the future. The Recruitment team ensures that its policies are fair and robust; however, termly reports have not been provided during this period. 100% of researchers are recruited through an open process as long as they are not named researchers on grants. There is mandatory recruitment and selection training for all staff, and relevant policies are also available in the handbook and on the intranet. | 1. Staff understanding of DORA will be measured during 2024-2027. SOAS' compliance with DORA principles will also be measured during this period and is built into the next action plan 2. To be measured during 2024-2027 through termly reports from the Recruitment team to the RCC. | Ongoing
| EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | 1. All new researchers are invited to participate in HR induction for new staff on their first day where they are made aware of policies and procedures that are relevant to them. 2. All new researchers are sent a New Staff Handbook by the Recruitment Team which contains relevant researchers information to policies and practices. New Staff Handbook created jointly by HRMT. 3. All new post-doctoral researchers are added to the online ECR space on MS Teams where practices relevant to their position are posted. An induction will be provided by the department and PI. This will be monitored via REC committee report every term. | carried over | 2. Handbook launched by end of T1, 2022/23 31/12/22. Invitations to HR Inductions ongoing 1 and 3. This will be reported on a termly basis T1,T2 and T3 31 December, 30 April and 31 August | Deputy HR Director - HR Services | 1. 95% of new research staff on 1+ year contracts receive New Staff Handbook within 3 months of starting their contract. 75% of research staff on 1+ year contracts attend HR Induction for New Staff. 2. 100% of new staff receive the Staff Handbook within their probation period. 3. 100% of post-doctoral researchers added to ECR space on MS Teams, which is co-owned by ECRs who use it as an online platform for peer review. |  | 1. Complete: All new staff are invited to an induction by HR in their first week. The HoD and line manager then also follows up with further relevant information. 100% of staff receive the relevant information through the intranet and/or induction. 2. Complete: New staff handbook shared with all new staff 3. Complete: The culture team regularly meets with HR and departments to ensure the ECR list is up to date. All ECRs receive information via the ECR Teams site, regular email updates from the Research Culture Manager, and regular catch-up meetings with staff members. From 2024-2027 there will also be a monthly newsletter in addition to one-off mailings. 4. Some delays: Inductions are happening but are not being monitored via the Research and Knowledge Exchange Committee; this needs to happen in the future. Our research culture focus groups revealed that there are quite wide discrepancies in terms of practice in relation to inductions by HoDs and line managers; these need to be harmonised and streamlined to achieve consistency in future. | 1. Staff are thoroughly inducted into processes and practices at SOAS, ensuring they are well supported. Qualitative feedback gathered through our research culture focus groups have revealed that some researchers feel that the HR inductions could be more robust so we have made this a key part of our forward-looking action plan. We have also introduced a new, termly induction for new staff with senior leaders of the university so that they are made familiar with broader SOAS strategies and welcomed by senior members of the community. 2. Staff can always refer to the Handbook when in doubt about processes and practices - 100% of staff receive the New Staff Handbook. 3. ECRs are regularly communicated with, through the ECR Teams site and frequent emails with opportunities about training, career development, and events. Regular in-person events are also held since we have found these are more conducive to building the cohort and community. This has made for a far more positive research environment and more holistic professional support service. 4. There is lots of positive feedback from those who have benefitted from strong induction experiences by their HoDs and/or line managers. This needs to be built on in future. | 1. No further action required 2. No further action required 3. No further action required 4. Ongoing
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression.
| EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | 1. Reward and Academic Promotion criteria are reviewed by Panel and EB/AB annually in T1 ensuring transparency and merit based procedures and criteria recognising the full range of researchers' contributions. Individual circumstances are incorporated into each procedure and considered as part of each process. Individuals on AER contracts are able to move to the T&R route via promotion using the SOAS Academic Promotion Scheme. Talent Pipeline programmes will be initiated in T1 of the academic year 22/23. 2. Establish a Task and Finish Group with representation from a department in each of the new Colleges, along with representation from research staff and the Research and Knowledge Exchange Office, to work through the operational implications of implement the San Francisco Declaration on Research Assessment (DORA). This group will report via a newly established Research Culture Sub-Committee to the Research and Knowledge Exchange Committee; its first objectives will be (1) to ensure the institutional expectations of DORA are captured in the terms of reference of the Research Culture Sub-Committee (2) To develop a communication plan to highlight the institution's formal signing of DORA (autumn 2022) and its implications. | Carried over | 1. Ongoing by T1 2022/23 31/12/22 for review and T3 of 2022/23 31/07/23 and then T3 2023/34 31/07/24for process 2. 30 September 2023 | Director of HR; Deputy Director of HR - Policy & Reward; Pro-Director of Research & Knowledge Exchange | 1. Reward and Academic Promotion criteria are reviewed by Panel and EB/AB annually in T1, in light of the DORA principles, ensuring transparency and merit based procedures and criteria recognising the full range of researchers' contributions. Individual circumstances are incorporated into each procedure and considered as part of each process. 30% more staff are able to apply to research focused career pathways, which opens up further opportunities, by comparing the number of applications from previous years with current numbers. 2. A broad range of impact measures, including qualitative indicators of research impact such as influence on policy and practice, will be taken into account in the recruitment of academic staff, resulting in a continued improvement in SOAS's Mean Ethnicity Pay Gap, which was 12.2% in 2020-21 compared to 14.0% in 2019-20. The aim is to decrease the figure to under 11% by 2024. |  | 1. Some delays: Our new Director of People who joined SOAS in 23/24 has undertaken a full review of the Promotions process this past year. There is a clear pathway for AER staff to cross over to the T&R route. There is an Academic Performance Framework which outlines the exact criteria for promotions and reward. 2. Some delays: DORA is included in the ToR for the Research Culture Committee but we have not had the capacity to develop the communications plan or the task and finish group. This will be incorporated into the forward-looking action plan for 2024-2027. We have, however, had multiple conversations across SOAS during this period about the importance of responsible metrics in research assessment, including at Senate, our most senior academic decision-making governance committee. | 1. Carried forward: In future the HR team will submit more regular reports in relation to quantitative data around promotions and reward. 2. The mean ethnicity pay gap is now 9.9%, representing a drop of 2.3% from 2020-21 showing that actions around inclusive recruitment, reward and recognition, and work to support the number of Black permanent academic staff and Black professional services staff at Grades 8, 9 and 10 have produced some results. DORA has been given visibility in the ToR for the RCC. | Carried forward
| EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers. | As E11 evidenced through termly reports and as EI3 | Carried over | Ongoing first report T2 2022/23 30/04/23 Reward and promotion by T3 2022/23 31/07/23 and then T3 2023/24 31/07/24 | Director of HR | As EI1 and EI3 |  | Complete: Managers receive training on inclusive recruitment and promotion. HR manages and updates policies to ensure this is robustly managed. | Data gathered from line managers reveals that recruitment and reward of researchers has been inclusive, equitable and transparent. There are beyond this several major "success stories" from this period e.g. around the USAWA postdoctoral scheme initiated by the Associate Director for Equity and Accountability, and through grant-funded projects such as the ERC project "African Screen Worlds". | No further action
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities.
| EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding. | HR induction will be conducted for all new starters every week and the Managers Induction for managers every month. The managers handbook will be given to all managers and provides an overview of HR policies and procedures and expectations of individuals in their employment. Monthly Managers' briefings are offered on people management topics as well as weekly surgeries | Not carried over | As ECI3 and ECM3 then ongoing. | HRBP and Recruitment and workforce reporting manager | as ECI3 and ECM3 |  | Complete : Managers' induction takes place 1st of every month (12 times a year) and for new starters every week if there are enough attendees per week. The handbook is automatically provided to all managers by HR and is on the staff intranet. Manager briefings have taken place at several points throughout the year, including Men's mental health (January 2024), Managing Stress (April 2024), and EDI (EAP). | Staff are thoroughly inducted on processes and practices at SOAS, ensuring they are well supported
| ER1 | Researchers ensure that they work in accordance with institutional policies, procedures and employment legislation, as well as the requirements of their funder. | 1. Employee relations cases for researchers will be tracked and reported on termly as part of the regular reporting for all cases. | Carried over | Termly 31 December, 30 April and 31 August Starts Dec 2022 | Deputy HR Director - Policy and Reward | Tracking of ER cases to monitor proportion of staff who are involved in ER cases |  | 1. Issues experienced: HR has not had the capacity to provide these reports during 2022-2024 due to the pressures from institutional change programme. The HR team have reviewed the process to ensure data collection is robust and reported to the correct channels from 24/25 onwards. There are rigorous policies in place for ensuring staff are aware of their roles and their requirements. All roles are recruited through approval at panel, following standard JDs. Mandatory training must be completed to pass probation, and research integrity training must be completed to be able to work on research projects. 2: Complete: SDRs and PRPs provide managers and mangers with clear objectives for their work. These have had very high completion rates at SOAS during this period. 3. Compete: Policies and procedures are listed on the intranet. The handbook is available to all staff. Briefings are also held and 1-1 support is available for line managers and employees through HR BP. 100% of staff are aware of this and are sent the information. | Staff are thoroughly inducted on processes and practices at SOAS, ensuring they are well supported. In 2023, 70% of staff completed their SDR. HR have identified that the previous system made for a long process and have instead moved to 'paperless' SDRs through the HR system (MyView) implemented in 2024 which is making the process more streamlined. Over 80% of research staff have completed a PRP (personal research plan meetings with colleagues' Dept RKE convenors).
|  |  | 2. Line managers ensure that their researchers meet the requirements of their role and work in line with institutional policies and procedures. |  | Termly 31 December, 30 April and 31 August starts Dec 22 | HRBP | 80% of research staff who respond to the survey agree that they undergo annual SDR and PRP reviews in addition to regular 1:1s with their line managers
|  |  | 3. All staff sent Staff Handbook, which includes policies procedures and legislation through information in Staff Handbook |  | Termly 31 December, 30 April and 31 August starts Dec 22 | Deputy HR Director - HR Services | 100% of staff are sent the staff handbook
| ER2 | Researchers understand their reporting obligations and responsibilities. | Line managers/Principal investigators, using normal management processes such as Induction, probation and Staff Development Reviews to ensure that researchers are aware of all requirements and oversee their work in this area. | not carried over | T3 2023/24 31/07/24 | HRMT | Low levels of complaint, via the institution's complaints and research integrity processes against researchers for not meeting obligations and responsibilities. Ensure a process for monitoring this is in place by 31 December 2022. |  | 100% must complete SDRs, training, induction and probation. In June 2024 a new SDR process was launched to ensure a more robust monitoring system. Training was provided every in May, June and July 2024 and a video shared with all staff via newsletter | The robust monitoring processes ensures equity across teams and staff, ensuring fairness and EDI
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews.
| EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | Offer enhanced line management training via Managers Development Programme, Monthly managers' briefings, HR Surgeries and the Managers' Handbook to all staff. Attendance and ratings can be measured by all staff. Project management training now available to all staff via LinkedIn Learning. | Carried over | ongoing reviewed Termly 31 December, 30 April and 31 August | L&D BP and Recruitment and workforce reporting manager | 100% of managers of researchers, HoDs and equivalent are offered line management and project management training opportunities |  | Complete: 100% of Managers receive a wealth of resources through internal training events, LinkedIn Learning, Managers' Handbook and staff intranet. Training is advertised in all staff bulleting. | HoDs and line managers of researchers have significant training and support in terms of developing their management skills.
| EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | At the annual TNA meetings with HoDs the L&D BP to emphasise that all managers are required to attend the sessions offered as part of the Managers Development Programme. All staff email and regular Staff Bulletin announcements that Annual Staff Development Reviews should be done each year; continue to provide training available to all staff on Effective SDRs | Carried over | TNA meetings with HoDs - annually by 30 September | L&D BP | 75% of Managers attend at least 1 of the Managers' briefings |  | Complete: Significant progress has been made on this front during 2023/2024 with our DVC for RKE meeting with people who haven't been promoted to explain how they need to improve. Our new Director of People has also developed an Institutional Culture strategy, which foregrounds excellent people management; he has also reviewed and updated the Promotions process through wide consultation. Our WAMS has also started to be implemented during this period leading to far greater transparency around workloads, and an easier system for managers to handle. SDR completions are very high, and there are frequent training opportunities; there is also the new online system which makes it easier to record completions. | Managers are well informed of best practices in people management.100% of managers attend Manager Inductions which take place each month. Managers also regularly undertake training and briefings. 100% of managers receive the Handbook. Promotion criteria are very clear in our Academic Performance Framework, and also communicated via in-person meetings at the beginning of each year.
100% of managers receive the Managers' Handbook
| EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care. | At induction all managers are advised to attend the sessions offered as part of the Managers Development Programme. Further training available via LinkedIn Learning. | not carried over | ongoing reviewed Termly 31 December, 30 April and 31 August | L&D BP | Measure number of managers of researchers who attend the training. 75% of research staff survey respondents (across all surveys) state that they feel supported by their line manager. |  | Complete: Training for managers in a range of topics is available through multiple routes including internal sessions, SDR training, LinkedIn Learning etc. A positive step forward in the period has been the launch of our new Black Managers' programme at SOAS, a tailored management training for marginalised groups, which had excellent reviews | A majority of staff at SOAS clearly feel well supported by their line manager. In our all-staff survey in 2022, 62% of respondents said they felt well supported by their line manager. In the 2024-2027 period we will be undertaking a research-specific survey to be able to disaggregate how research-only staff specifically feel about their line managers.
| EM4 | Managers actively engage in regular constructive performance management with their researchers. | 1. Bi-monthly training sessions on Performance Management will continue to be offered as part of the Managers Development Programme 2. Launch of Managers Handbook in Term 3, 2021/22 (31/07/22) will provide guidance on performance management | not carried over | From end of Term 3, 2021/22 31/07/22 | HRBP Team | 1 and 2. 70% of staff reporting awareness of performance management processes in all staff survey |  | Complete: Training for managers offered through as part of internal training package and available to all staff who manage others. Complete: Launch of Managers' Handbook which is shared widely through several different channels. | A majority of staff at SOAS clearly feel well supported by their line manager. In the future we need to find out how research-only staff feel about their line management. n our all-staff survey in 2022, 62% of respondents said they felt well supported by their line manager, suggesting that a majority of line managers are well informed of performance management processes. The new Managers' Handbook has provided a very important resource to all line managers, bringing much greater clarity.
| ER3 | Researchers positively engage with performance management discussions and reviews with their managers. | PRPs will remain mandatory for staff on 0.4 FTE as a research mentoring tool to support researchers to produce their best possible work, to have the greatest possible impact, and to generate the funding that can sustain and expand the originality, significance, and reach of their research, and will be rolled out to all research-active staff. | not carried over | Ongoing, reported end of T3 31 July each year to REC | Department Research and KE Convenors and Pro-Director Research & Knowledge Exchange | 80% of staff engage with the PRP process and indicate in focus groups to find it a useful exercise |  | Completed: Feedback from staff reveals that people feel that PRPs are an extremely positive and helpful tool in terms of focusing in on their research work, plans, and achievements in particular (whereas the SDR process offers a more universal overview). Uptake in most areas has been high, although a small number of areas have been identified where provision / uptake has been poor. PRP completion during 2022-2024 were monitored by liaising directly with Dept RKE Convenors. | Over 80% of research staff have completed a PRP (personal research plan meetings with colleagues' Dept RKE convenors). | Completed
Job security
The aim of this obligation is to improve the job security of researchers.
| EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | HRBP Team will ensure managers carry out an end of contract meeting with researchers to discuss redeployment opportunities. Discussions will be recorded on the end of contract form and shared with HRBPs. The HR Operations team will produce yearly reports on the redeployment of researchers which will be monitored by the HRBPs. | not carried over | Annually in July by 31/07 | HR BP, HR Services | 1. Compare total number of completed forms submitted for all staff versus the total number of researchers whose contracts have come to an end, to identify the number of redeployment discussions that have taken place with researchers. 2. Produce an annual report on the total number of redeployments in SOAS by the end of the academic year and cross check this with the number of redeployments for research staff to ensure that 100% of research staff are afforded the redeployment opportunity. The targeted impact is that there is an equality of opportunity for redeployment across all staff groups including research staff. |  | 1. Experienced issues: Due to resourcing in the HR team these reports have not been created. However, the RKED and Research Culture team are working with the Director of People to ensure that this is central to our actions going forward (see forward-looking action plan) in terms of trying to support post-docs in finding further grants to apply to, and creating bridging contracts while they await outcomes. 2. All academics at SOAS are given the opportunity to have a research mentor through our new Research Mentoring Framework. 3. Experienced delays: We have made excellent progress in terms of the development of the Research Hub, with the Lady David Gallery space currently under refurbishment that will be completed during Term 1 of 24/25 and will provide a wonderful space for PGRs. The Work Bank is still in development due to understaffing and staff turnover in the Doctoral School during this period. | Informal data on the onward journeys of our post-docs have revealed that while there have not often been deployment opportunities at SOAS (except with the FLF), many of our post-docs are going on to secure prestigious permanent positions after their time with us (e.g. the Usawa post-docs, and those on the African Screen Worlds ERC project). In 2022-2024 there were 30 Academic promotions this year – including 2 pending receipt of the HEA certificate | Ongoing
|  |  | HoDs to assign mentors to ECRs and post-doctoral researchers and ensure that they have personal research plans so as to provide support for career development. Department Research and KE Convenors to play a role in monitoring the use of short-term contracts in the department for research and avenues for redeployment. | not carried over | 2023-01-31 | Department Research and Knowledge Exchange Convenors and HoDs | Reduce the practices of casualisation that intensified in the last years to 4% and mandate a near-to-full cessation of casual employment outside of certain strictly limited contexts (e.g. to cover parental leave, and in provision of teaching and other opportunities to doctoral researchers).
|  |  | Development of a 'work bank' to facilitate and make more equitable the assignment of paid work for SOAS doctoral researchers and a dedicated Research Hub space combining quiet workspace, informal meeting and social space, as well as exhibition and event space. | not carried over | 2024-07-01 | Head of Doctoral School, HR Business Partner Team | Increase in the employment opportunities of self-funded doctoral researchers as measured via the PRES survey. Increased PGR student satisfaction rate to 80% in the March 2023 PRES survey
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it.
| PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | 1. Provide a guide to the broad nature of professional development activities that researchers can engage with 2. Implementation of WAM - The new WAM recognises that researchers engage with professional development training 3.Communication with HoDs and College/Department Research & KE Convenors to ensure that professional development expectations are included in SDRs and PRPs | Carried over | 1. T2 2022/23 30/04/23 2. T1 2022/23 31/12/22 3. Communication and engagement with HoDs and College/Department Research and KE Convenors in T3 2022/23 31/07/23, ahead of SDRs and PRPs | 1. Research and Knowledge Exchange Directorate 2. Provost/Chief Operating Officer 3. HR | 1. Guide introduced 2. WAM fully implemented 3. Feedback from SDRs and PRPs; researchers report to have time to engage with professional development |  | 1. Complete: The RKED and L&D teams clearly communicate all training and development opportunities to all staff, and especially ECRs (through the ECR mailing list). Staff have thus had a wealth of opportunities to pick from for their 10 days of professional development, including the Aurora women's leadership development programme (19 staff have been involved), the new Black managers' programme (12 staff have been involved), the BMEntoring programme (16 staff have been involved), LinkedIn learning programmes, and much more. The Careers team also organises and communicates opportunities for PGRs and ECRs, including those beyond academia. 2.Complete: The WAMS was developed and piloted during the 22/23 academic year and has been fully implemented during 23/24. It has been communicated via in-person meetings throughout SOAS and via written communications. 3. Complete: SDR and PRP templates and discussions include professional development, and actively encourage staff to specify what future training they would like to undertake as well. | Data shows involvement across a range of high profile external professional development schemes including Aurora women's leadership development programme (19 staff have been involved), the new Black managers' programme (12 staff have been involved), the BMEntoring programme (16 staff have been involved). Feedback on involvement in these schemes has been extremely positive. WAMS is enabling researcher development time to be allocated and earmarked. | No further action
| PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | 1.Analyse the new staff development platform (Inkpath) to assess take up of professional development 2.L&D BP to run reports termly to assess engagement in development activities of researchers and their managers | Carried over | Termly starting T2 2022/23 Termly 31 December, 30 April and 31 August | L&D BP | 1 and 2. Research Culture Sub-Committee receives termly reports from Inkpath and a description for the spring term meeting of 2022 of the reporting capabilities of system. |  | Experienced issues: L&D have started to provide Inkpath data but need to ensure this comes to the RCC termly. There have been issues with how the platform records engagement with activities so HR are reviewing a new platform to be implemented in 18 months. |  | Ongoing
| PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development. | as PCDI1 | Carried over | T3 2023/24 31/07/24 | L&D BP and Research and Knowledge Exchange Directorate | As at PCDI1 for research staff survey respondents and 75% of Managers confirm that they have allocated 10 days for their researchers via feedback to L&D BP |  | Complete: WAMS policy includes professional development time. | 100% of staff are aware of the WAMS policy and the need to allocate 10 days of professional development to researchers. | No further action
| PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year. | L&D BP to arrange career development workshops and email researchers to advise they are available | Carried over | Termly beginning T2 2022/23 30/04/23. Annual report on number of attendees in T3 2022/23 31/07/23and T3 2023/24 31/07/24 | L&D BP | Three workshops run per year. Attendance numbers improve as a % of total number of researchers by 10% over first year and a further 10% over second year. Satisfaction levels of participants are good or better for 75% of attendees. |  | Experienced delays: Informal feedback from our research culture focus groups and start of year and end of year events with researchers suggest that they are taking responsibility for making the most of their 10 days of professional development, and are aware of all the opportunities on offer through the RKED, L&D and Careers teams at SOAS. An informal survey was also run with researchers at the end of 22/23 to gather their preferences for research development training events during 23/24. | Work to continue to gather feedback (both formal and informal) from researchers on their development | Ongoing
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews.
| PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers. | L&D BP to continue to offer Effective SDR workshops; continue to offer information and guidance on SDR completion on SharePoint pages; which also signposts managers to LinkedIn Learning for further resources | Carried over | Annually T3 2022/23 31/07/23 and T3 2023/24 31/07/24 | L&D BP | HoDs report SDR completions annually to L&D BP (currently HR BP due to gap in replacing current L&D BP). Percentage of research staff completing an SDR is comparable to the rate of return for other staff groups. |  | Complete: The training is run monthly with an average 8 colleagues in attendance. It is run both for line managers and managees. There are increased sessions closer to the deadline for SDR completion (31 July). A new SDR system was implemented in July 2024, linking to the current HR system, making everything more integrated. | Data on SDR completion via the new online system will be available from summer 2024 onwards | No further action
| PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews. | L&D BP chases HoDs to report SDR completions to L&D BP | Carried over | Annually T3 2022/23 31/07/23 and T3 2023/24 31/07/24 | L&D BP and HRBP | Number of SDR completions goes up by 5% as reported by HoDs to L&D BP (in interim gap will be the HR BP) |  | Complete: Work to encourage the uptake of SDRs across the institution has been ongoing. | Completion rates have increased in 2023/2024 with an average of 77.57% of SDR completions across our 10 academic departments where researchers sit. | No further action
| PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually. | L&D BP reminds line managers of researchers of the importance of holding regular career development discussions, including SDRs and PRPs | Carried over | Annually T3 2022/23 31/07/23 and T3 2023/24 31/07/24 | L&D BP; Department Research & KE Convenors and HoDs | HoDs report SDR completions annually to L&D BP (currently HR BP due to gap in replacing current L&D BP) Department Research & KE Convenors report anonymised PRP outcomes annually to HoDs and Pro-Director Research & Knowledge Exchange, feeding into College-level strategic planning |  | Complete: PRPs are not compulsory in all Depts, but many colleagues choose to do these so there is high engagement; they are usually run by Dept RKE Convenors. All research-only ECRs are encouraged to use this opportunity to discuss their research. | SDRs have increased (see above). PRPs are also very popular, even though they are not compulsory (more than 80% completion). | No further action
| PCDR4 | Researchers positively engage in career development reviews with their managers. | L&D BP reminds researchers of the importance of holding regular career development discussions, including SDRs and PRPs, and invites all researchers to attend one of the regular 'Effective SDRs' workshops. Expand understanding of the breadth of opportunities that lead to effective researcher development through PRPs and SDRs. | Not carried over | annually T3 2022/23 31/07/23 and T3 2023/24 31/07/24 | L&D BP | Number of SDR completions goes up by 5% as reported by HoDs to L&D BP (in interim gap will be the HR BP) PRPs rolled out in 2022/23 to all research-active staff |  | Complete: In addition to an increase in SDRs and PRPs, and better training in completing these, our new research mentoring framework offers researchers at all levels the chance to regularly discuss their work and progress with someone who is *not* their line manager, which has additional benefits (4 hours a year are offered by mentors). | See above | No further action
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience.
| PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | 1. L&D BP and RKE Directorate to review online course provision for Early Career Researchers 2. To provide promotion workshops for each career stage | Not carried over | Term 3 2023 31/07/23 | L&D BP & RKED | 1. The Impact will be measured by the guidance and provision of a line of set up courses 2. The Impact will be measured by the creation of suitable training for each career stage. |  | 1. Complete: A solid range of training was provided by the RKED, L&D, and the Careers team in 23/24, with positive feedback from attendees. The 23/24 offer has acted as a base for developing an even more robust, weekly training framework for 24/25. 2. Complete: In March 2024, the Culture team ran separate workshops for ECR and mid-career researchers to discuss a range of topics, including promotion. | Feedback showed that the most popular among ECRs were two "Pitching for Publishing" sessions (24 attendees across both). Research mentee training was also offered in Jan and March (20 attendees). There was 100% attendance at these workshops (15 from each career stage, 30 total). We received excellent feedback on them. | No further action
| PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications. | 1. Professional and career development planning are embedded in institutional culture through PRPs 2. L&D BP and L&D Adviser to provide information on how Inkpath can be used to build portfolios of evidence; this can be downloaded by users any time for the duration of the platform's life (even after they leave SOAS) | Not carried over | T3 2022/23 31/07/23 and T3 2023/24 31/07/24 | L&D BP and L&D Adviser | 1. 50% of research staff survey respondents agree that they know how to set up a portfolio in Inkpath. Increase in Y2 to 70% of respondents 2. To maintain 80% take up of PRPs, rolled out to include everyone with research in their contract |  | 1. Complete: See PCDM1 2. Experienced delays: We have not had the capacity to measure the number of portfolios created. However, HR have developed 'How to' videos on Inkpath showing researchers how to export training and sent this out to all researchers. These have also been shared in the staff bulletin, at trainings and briefings. Independently, the Careers team has also been supporting PGRs and ECRs with monthly sessions on developing their CVs. | Further data collection on the uptake of PRPs will be taken forward in the 2024-27 plan (during 2022-2024 they have been monitored through the Research Culture team emailing the Dept RKE Convenors who run the PRPs to check up on completions). | 1. No further action 2. Ongoing
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities.
| PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | 1. SOAS is implementing the workload allocation model to ensure time for research, embedded across all departments 2. SOAS is strengthening academic leadership as we move to a new college structure with updated governance structures, which provide leadership development opportunities 3. To continue the Personal Research Plans (PRPs) for individual researchers within the Departments | Not carried over | 1. 30 April 2023 2. Leadership roles in place 31 Jan 2023 3. PRPs completed by 31July 2023 | Research and Knowledge Exchange Directorate | 1. All departments use the new Workload allocation model 2. College Heads and Research and KE Convenors are in place in Jan 2023 3. Maintain 80% completion rate of PRPs; PRPs are done by all departments whilst expanding to cover all staff with research responsibilities in their contract. |  | 1. Complete: The WAMS was developed and piloted during the 22/23 academic year and has been fully implemented during 23/24. It has been communicated via in-person meetings throughout SOAS and via written communications. 2. Complete: The new structure was introduced in September 2022 and has been successfully implemented since then, with a far more robust governance system in place through committees (all with representation by researchers), and with many opportunities for leadership development. 3. Complete: See PCDM1 |  | No further action
| PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours. | 1. Professional development allowance will be fully embedded in the new Workload allocation model. We will use this instrument to enforce the time allocation for professional development. 2. HR and Research and Knowledge Exchange Directorate identify suitable leadership training courses and provide training in house or from external providers. | Not carried over | 2023-07-31 | HR & Research and Knowledge Exchange Directorate | 1 and 2. 10% staff attending external training courses (Advanced HE, ARMA) annually, and 30% attending internal training courses annually |  | 1. Complete: 10 days staff allowance for staff development is implemented in the WAM policy, communicated via staff intranet 2. Complete: 19 women have taken the Aurora women's leadership development course, and 12 colleagues have taken the new internal Black managers' course (which has a strong leadership dimension). Several senior staff have also taken the AdvanceHE Senior Women's Leadership Development programme. In the next period we will encourage more staff to undertake leadership training, seek out and publicise more widely further opportunities (e.g. the AdvanceHE leadership training for more junior staff), and also develop more of our own in-house resources (we have started developing a suite of in-house videos about research leadership). | The policy is on the staff intranet which 100% can access 19 women have taken the Aurora women's leadership development course, and 12 colleagues have taken the new internal Black managers' course (which has a strong leadership dimension). Several senior staff have also taken the AdvanceHE Senior Women's Leadership Development programme. | No further action
| PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development. | 1. As we move to the new college structure, all academic leaders (Heads of College, Heads of Department and Convenors of Research and Knowledge Exchange at College and Department level) will have an induction and a training session. 2. Bespoke HoD training on RKE policies and processes provided by the RKED | Not carried over | 2023-01-01 | 1. HR 2. Research and Knowledge Exchange Directorate | 1. Heads of Colleges and Convenors of Research and Knowledge Exchange at College and Departmental level receive induction and training by Jan 2023 2. 100% of HoDs and PIs engage in training on RKE policies and procedures by Jan 2023 |  | 1. Complete: All new role holders as part of the new leadership structure have been given inductions and training. 2. Experienced delays: Due to resourcing issues, this has not been possible and will be rolled over to the 2024-2027 action plan. |  | 1. No further action 2. Carried over
| PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills | 1. Researchers engage with opportunities to develop their research profile and showcase their research through a more dynamic web presence, by updating their PRPs annually, taking part in media and impact training, producing high-quality visual, audio and written communications, depositing their research outputs in the revamped Open Access repository, and participating in the SOAS Festival of Ideas every two years 2. Researchers take up research and KE training 3. Postdoctoral researchers take up mentoring on offer | Carried over | June - 2024 | Pro-Director Research & Knowledge Exchange and Research and Knowledge Exchange Directorate | 1. Researchers to review opportunities posted by the RKED and discussed with their line manager. By 2022-23 90% of researchers have a ORCID iD and a Google Scholar profile 2. Establishing a baseline of uptake of research and KE training in 2022-23 and increasing this with 10% in 2023-24 3. Mentoring policy is fully implemented at departmental level and 100% of researchers who request being mentored are allocated a mentor by their department |  | 1. Complete: There is a dedicated Teams site and listserv for ECRs through which the RKED communicates all of these opportunities. We have also encouraged cohort-building and engagement through start-of-year welcome events and end-of-year celebration and reflection events. There is also a new institutional website where researchers are encouraged to keep their profiles updated and to upload their research onto the institutional repository. In future, we will continue encouraging and supporting researchers to develop their online profiles in a range of ways. 2. Complete: Range of training developed and provided. 3. Complete: All research-only ECRs were written to and strongly encouraged to sign up for a mentor through the new scheme | Due to resourcing issues, we have not been able to measure take-up, but will do so in future. In the first year 50% of mentees were from this group of ECRs. We will continue to monitor this uptake. | Ongoing
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
| PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | 1. L&D BP to continue to offer mentoring training and job shadowing opportunities both internal and external. 2. Careers Service to continue to offer career advice and explore secondment opportunities 3. Encourage researchers to apply for Impact Acceleration Accounts and other funding streams that offer short-term public, private and third sector placement opportunities and offer support to build this into research grant applications | Not carried over | Annual report starts T3 22/23 31/07/23 and survey T3 23/24 31/07/24 | L&D BP and RKED | 1. and 2. Annual L&D Report shows increased uptake of internal mentoring cross referenced to attendees of careers training sessions. 60% of research staff survey respondents agreed that they have considered opportunities to develop their awareness and experience of the wider research system 3. Number of funding schemes, relevant grants successfully obtained and number of placements tracked |  | 1. On track: The L&D team have widely publicised the OutsideInsight job shadowing programme to staff since 2023/2024, but there has not been a large amount of take-up. We plan to increase this in future. We have realised that the Careers team is doing as much on this front as L&D and so this area is being merged in the forward-looking plan. As explained above, we now have robust mentoring and training programmes for researchers in place, through which researchers can also explore non-academic careers. 2. Complete: The Careers team has been offering monthly training sessions for PGRs and ECRs on CVs and networking throughout this period. They also hold many events open to these groups that allow them to explore careers beyond academia. We will continue to enhance collaboration between the Careers team, L&D and the RKED in 2024-2027 since this convergence occurred late in this period. 3. Experienced delays: The DVC for RKE and Director for RKE have been encouraging researchers to apply for Impact Acceleration Accounts throughout this period, and there has been some success on this front. | ESRC Impact Acceleration Accounts award rapid response and strategic grants of £2,500 to £10,000 that support co-production of knowledge and impact-oriented outputs published through staff channels to encourage staff engagement. IAA strategic grant received 19 applications, 7 successfully awarded of which 3 were ECRs. | No further action
| PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments. | 1 . To improve communication with PIs and supervisors, ensuring they are fully aware of the training and development activities on offer. Managers highlight the expectations of the Concordat for the Support of Researchers (i.e. a minimum of 10 days of professional development training). In particular, they encourage the exploration of a wide range of career opportunities. 2. In line with SOAS's KE Concordat Action, KE capacity development building for staff and students is a priority, aiming to amplify the researchers’ voice, embed KE more fully in the research cycle, and open up career development trajectories by actively promoting KE training opportunities to researchers; actively seeking to embed the more technical skills of KE within our community, including IP and public engagement, as well as radio and video production and working with external suppliers and developing our bespoke training and guidance for researchers in various forms of external engagement in exploring and preparing for a diversity of careers. | carried over | 1. Ongoing starting T2 2022/23 30/04/23 and for survey T3 2023/24 31/07/24 2. Ongoing starting T2 2022/23 30/04/23 and for survey T3 2023/24 31/07/24 | Research and Knowledge Exchange Directorate | 1. 70% of research staff survey respondents agree that their managers have supported them to explore and prepare for a diversity of career 2. 60% of research staff survey respondents agree that they have undertaken mentoring or secondment opportunity or careers training |  | 1. Completed: The Research Culture team, wider RKED, and L&D work collaboratively to inform staff of the carried development opportunities at the school via the staff intranet, direct emails, all staff bulletin, and cascade through RKE Convenors, line-managers of researchers and HoDs. All research staff are informed about the 10 days allocated for development activities via the WAM, staff intranet, line managers and Personal Research Plans. L&D have run annual career events, highlighting the carried career opportunities for researchers (industry events and CV workshops). 2. Experienced delays: RKE attends regular academic committees to share information and promote the service, during 2023-24 at least one member of RKE attends the termly academic staff meetings for the departments. Due to resourcing issues, it has not been possible to roll out the full suite of training and resource offering for Enterprise initiatives. This has been reviewed with our resource and rolled over to the 2024-2027 action plan | 1. A survey specifically for research staff was not carried out during this period, so we cannot report on the specific success measure but through workshops in March 2024 with Research staff the team gained valuable insight into improving our communications. Further to this, L&D activities have had good sign-up to workshops and training, showing that this is being communicated to a wide range of staff. See E16. The team is developing a benchmarked survey for research staff. The team will also continue to run regular workshops to gain insights into our strategy. In 2024 SOAS will be launching a new intranet, and the Research Culture team and L&D are working closely to produce clear content collaboratively to improve communication with staff. 2. A survey specifically for research staff was not carried out during this period, so we cannot report on the specific success measure but through workshops in March 2024 with Research staff the team gained valuable insight into developing our KE offer, which has informed our new plan for Researcher Development to launch in autumn 2024. | No further action
| PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments. | 1. L&D BP to continue to offer mentoring training and job shadowing opportunities both internal and external. 2. SOAS Careers Service will continue to monitor, review, adapt and develop relevant resources and guidance, including 'Resources for PhDs and ECRs' pages, which include guidance on both academic career pathways and other professional routes. The Careers Service will continue to provide access to SOAS Connect, an eMentoring platform designed to help connect SOAS alumni and students around the world for peer-to-peer careers advice and guidance. During all Careers workshops participants are encouraged to connect with each other and build their networks. SOAS Careers will also deliver a specific workshop on 'Presenting and Networking at Conferences' which includes guidance, support and resources on networking generally. | carried over | as at PCDI5 | L&D BP and Careers Service | 1. Annual L&D Report shows increased uptake of internal mentoring cross referenced to attendees of careers training sessions. 60% of research staff survey respondents agreed that they have considered opportunities to develop their awareness and experience of the wider research system. 2. Number of applications to internal competition for placements under relevant funding schemes (e.g. ESRC Impact Acceleration Account etc). |  | 1. Complete: See PCDI5 2: In the period 2023-24 L&D In 2023-24 extended our programme of specialised workshops for PhDs, ECRs and PhD applicants to eleven events across three semesters. They introduced 45 minute researcher specific guidance appointments following on from these workshops for attendees to speak with a specialist about their specific concerns. 10 sessions, ranging from academic CV writing; academic year planning. 100% attendees were positive about the training Select feedback from workshops: '[course leader] was passionate about the topic. Because of that passion she was able to convey very helpful pointers. I'm very new to the possibility of teaching roles and this was very insightful.’ 'I would most certainly recommend this event. This event opens up the whole range of ideas, jobs, skills set, experience, etc. needed to approach the job market (academia or otherwise).’ | 2. Impact Acceleration Account grant received 19 applications, 7 successfully awarded of which 3 were ECRs. In 2023 SOAS received its first KTP and to date a second KTP is underway, both organisations and researchers report that the projects are going well and greatly benefiting to the parties involved. This has been a huge milestone for SOAS The associate gets £4,000 for training | No further action
| PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation. | Researchers are encouraged to engage with the new Knowledge Exchange and Research Impact team, which will be established in Autumn 2022 as part of the Research and Knowledge Exchange Directorate, and the SOAS-based lobbying group Influencing the Corridors of Power (ICOP), which disseminates academic research among policy makers. They will be invited to training events and drop-ins. | not carried over | 2023-07-31 | Research and Knowledge Exchange Directorate | An increase of 50% of researchers who have engaged with knowledge exchange, as measured by the institution's scorecard indicator for knowledge exchange activity; increase of 100% of postdoctoral researchers applying for funding via the School's Impact and KE fund (IKE) |  | Complete: There has been wide publicising of the new KE and Impact teams in the RKED to all staff. During 2023-24, three training sessions were run on impact development. Training on research commercialisation was also offered. More of such training will be offered in the future. | Attendance at some sessions was quite low (impact development had 5 attendees, as an example) however work to promote and encourage attendance will be a priority for the next action plan. College-wide introductory sessions on impact geared towards ECRs are being planned for 24/25.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
| Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
| 1 |  |  |  |  | AB | Academic Board
| 2 |  |  |  |  | AER | Academic Education-Focused Route
| 3 |  |  |  |  | BoT | Board of Trustees
| 4 |  |  |  |  | CHASE DTP | The Consortium for the Humanities and the Arts South-east England Doctoral Training Programme
| 5 |  |  |  |  | DORA | San Francisco Declaration on Research Assessment
| 6 |  |  |  |  | DS | Doctoral School
| 7 |  |  |  |  | DSMG | Doctoral School Management Group
| 8 |  |  |  |  | EAP | Employee Assistance Programme
| 9 |  |  |  |  | ER | Employee Relations
[6 empty] | FTE | Full-time equivalent
[6 empty] | HRD | Human Resources Directorate
[6 empty] | HRMT | Human Resources Management
[6 empty] | KE | Knowledge Exchange
[6 empty] | L&D BP | Learning and Development Business Partner
[6 empty] | PGR | Postgraduate research student
[6 empty] | PRES | Postgraduate Research Experience Survey
[6 empty] | REP | Research Ethics Panel
[6 empty] | RIAS | Research Integrity Annual Statement
[6 empty] | RKE | Research and Knowledge Exchange
[6 empty] | RKED | Research and Knowledge Exchange Directorate
[6 empty] | RSA | Research Students' Association
[6 empty] | SDR | Staff Development Review
[6 empty] | T&R | Teaching & Research
[6 empty] | ToR | Terms of Reference
[6 empty] | TNA | Training Needs Analysis
[6 empty] | WAMS | Workload Allocation Management System
[6 empty] | PRP | Personal Research Plan

## Funders obligations
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions
Employment
Job security
The aims of these obligation are to improve the job security of early career researchers.
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to do so.
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Guidance
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: | Enter relevant information |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | Enter relevant information |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | Enter relevant information |  |  |  | Research staff |  |  | These are your primary beneficiaries, and should be prioritised across the action plan - both by being targeted with actions and evaluated through success measures.
| Institutional context: | Enter relevant information that helps frame the action plan and the intended institutional audience. For example, this box can be used to disclose the research intensiveness of the institution, providing a justification for the breadth/depth of the actions disclosed. |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Describe here your actions/interventions for meeting the obligation, referring to actions elsewhere in the action plan if preferred. | Has the action been carried forward from a previous action plan? "yes" / "no" | Indicate a month and year | Name all key parties responsible for the action(s) and success measure(s) | Describe here your success measure(s), used to report against the intended impact for researchers and incorporating researchers' views wherever possible. | Describe here any supplementary information. | Describe here a written summary of the progress made against the obligation, taking a broad view of the people and/or organisational development that may have occurred. | Provide evidence that directly reports against all success measures described previously. | Indicate the next steps for the action from the following options: "ongoing" (if the deadline is scheduled in the future), "carried forward" (if the action was not completed as planned by the initial deadline) or "no further action" (accompanied by a brief explanation).
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | Institutions planning actions for specific funders' obligations can insert these obligations into the relevant section of the institution template.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | Use these spaces to provide links and references for information provided in the action plan. |  |  |  |  | Use these spaces to describe abbreviations and
2 | [5 empty] | terms used in the action plan.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
N.B. This section is for reporting only, and should not be completed prior to the beginning of the action plan's term.

## Tips
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff |  |  | Only include institutional audiences considered to directly benefit from the action plan, remembering that research staff should be prioritised.
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers. Our internal evaluation revealed that researchers feel the university strategic priorities do not reflect their own (62% in a consultation said that they felt disconnected from the university's recent 'Strategy 2030'). Heads of Faculties also report from conversations at committee meetings that researchers feel the university's strategic priorities are not entirely aligned with the reality felt in specific research disciplines. Optional: Institutions can use this space (if desired) to discuss the context that frames the actions and success measures disclosed.
ECI1 | Ensure all relevant staff are aware of the Concordat
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | Providing actions for every obligation is not mandatory, although action plans should aim to target those in their priority areas and/or those highlighted by researchers during the internal evaluation.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Host programme of Faculty- and institution-wide workshops on research culture, capturing local and broader views on key themes in research and reflecting these with the institution's 'Strategy 2030' priorities. Gather a comprehensive range of anonymous views from research staff on how they feel their Faculty research environment compares to the institution as a whole through quarterly Faculty pulse surveys. | no yes | Jul-23 Being specific (rather than only stating "ongoing" or "annually") indicates that reporting has been properly scheduled and that actions are timebound. May-23 | • RCWG • Heads of Faculties • PVC-RI • Faculty-HR • RCWG Broad and specific responsibility can show a joined-up approach to working, connects institutional stakeholders around the Researcher Development Concordat and also shares the workload. | • Host quarterly workshops for each Faculty, and biannual institutional workshops. Success measures like this (i.e., "action completed") are acceptable but should be complemented by other measures that show the impact of the action. • Drafting of workshop reports led by research staff attendees, and reports instated as a standing agenda item at Faculty committee meetings. • At least 30 research staff attendance (on average) at Faculty workshops. Positive post-event feedback from at least 80% of research staff attendees. • At least 40% of research staff (on average) across all 5 Faculties respond to Faculty pulse surveys. Success measures like these allow institutions to qualitatively and quantitatively assess progress against the obligation. Note the words underlined in the obligation and consider how the success measures could align with these. Setting numerical (i.e., SMART) targets can provide an unambiguous benchmark to report progress against in the future. |  | Programme of workshops conducted digitally due to ongoing COVID restrictions (1). Attendance was encouraging, with a good number of research staff joining and contributing to both discussions and the chat function. Research staff were less engaged in the reporting of the workshops than hoped, partially attributed to the less stimulating setting of online events. Feedback from research staff attendees was very positive, and both this feedback and the workshop discussion points were fed into Faculty committee meetings. In one instance, this prompted a Head of Faculty to set up focus groups to explore one particular issue more closely. Faculty pulse survey engagement was encouraging, albeit variable across the Faculties. The findings and trends will help inform future Concordat action plans and the university's Research Culture manifesto. By describing the action's progress in narrative form, institutions can explain success in greater detail, or mitigate challenges experienced, by providing helpful contextual information. | • All 5 Faculties' workshops held quarterly, as well as two workshops held at an institutional level. • Workshop reporting only partially led by research staff across the Faculties. All Faculty committees successfully instated research culture reports as an agenda item. • 34 research staff attended each workshop on average. 86% of research staff attendees gave positive post-event feedback, with 84% saying they "found the workshop to be helpful". • 38±3% of research staff responded to pulse surveys across all Faculties, although some only received 35% research staff response rates. Ensuring you report against all success measures provides a better assessment of the impact achieved and shows commitment to researchers that the institution cares about their views and behaviour. | no further action (action now considered normal business) After selecting from one of the set responses in the column header, institutions can briefly indicate the rationale for this decision (e.g., "action successfully embedded" or "action delayed, partially completed").
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Even if no action is intended/needed, it is encouraged to include success measures that show how different stakeholders engage with/benefit from other actions. |  | Jul-23 | • RCWG | At least 70% of research staff answering CEDARS q42.4 ("feel included in your immediate research environment/group") agree or strongly agree (CEDARS 2021: 62%) | Survey response rate in 2021: 16% research staff (n=147) Optional: This space can be used to provide details not suitable for the other columns. For example, you can add information relevant to an action and/or a success measure to help demonstrate feasibility. | CEDARS response rate improved considerably after a campaign of targeted communications. This coincided with less positive responses for q42.4 than anticipated, suggesting that the university is now successfully reaching a previously 'silent' yet dissatisfied group of research staff with the survey. | 64% of research staff responded agree/strongly agree for CEDARS q42.4. 22% of all research staff (n=202) responded to CEDARS.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and Supplementary Information (more rows can be added) |  |  |  |  | Abbreviations and Glossary (more rows can be added)
1 | www.university.ac.uk/researchculture/researchcultureworkshops/summary |  |  |  | PVC-RI | Pro-Vice Chancellor for Research & Innovation
2 | Using these spaces can help keep the main body of the action plan as concise as possible. |  |  |  | RCWG | Research Culture Working Group
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
This sheet gives a hypothetical response to a group of obligations under Environment and Culture > Awareness and engagement.
Tips and advice are shown alongside to highlight how to organise actions and success measures to deliver the most impact, as well as to demonstrate a transparent and compelling approach to reporting on progress and the original success measure.
For brevity, the remaining obligations have been omitted from this 'Tips' sheet.