## Template for institutions
| HREiR Action plan template (2024-2027) | [6 empty] | #VALUE!
Details
| Institution name: | SOAS University of London |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | 5 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | 2024-09-20 |  |  |  | Research staff |  | 63
| Institutional context: | SOAS University of London is a small, specialist Higher Education institution, focused on research and teaching about Africa, Asia, and the Middle East. There are approximately 5,500 students enrolled across undergraduate, masters, and postgraduate research degrees. SOAS is internationally recognised for its specialist expertise in the arts, humanities, and social sciences and is a research-intensive institution. |  |  |  | Postgraduate researchers |  | 465
[6 empty] | Research and teaching staff |  | 256
[6 empty] | Teaching-only staff |  | 28
[6 empty] | Technicians |  | NA
[6 empty] | Clinicians |  | NA
[6 empty] | Professional support staff |  | 29
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat. | 1. Include information on the Concordat in all Research staff training sessions. 2. Dept RKE Convenors to share the Concordat with all staff at the start of every academic term, at Department meetings. 3. The Line Managers of ECRs on research-only contracts share Concordat when ECRs begin post. 4. During migration to the new staff intranet, ensure Concordat and HREiR logo, links and information are prominent within the Researcher Development section of the site. | 1. Carried over 2. Carried over 3. New 4. New | June 2025 Sep 2025 Sep 2025 Sep 2025 | RKED RKE Convenors Research Line Managers RKED | 1. Researchers Survey (CEDARS 2025) shows that at least 40% of respondents report that they have heard of the RD Concordat. 2. Gather feedback through workshops and other fora about researchers' awareness and understanding of the RD Concordat. | 1 and 2. Sector benchmarked CEDARS data is at 53% for this question (2023 report).
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | 1. Work with the Staff Intranet project team to ensure all relevant policies are clearly linked in a revised Researcher Development Hub intranet site with signposting from other relevant areas. 2a. EDI team to complete EDI impact assessment of all relevant policies. 2.b Build processes to ensure the consideration, and involvement, of research staff is integral to the development and revision of policies within the Human Resources directorate 3. Ensure the timely and transparent communications of policies and practices to researchers through multiple channels, utilising proven College comms structures to support dissemination. 4. Improve feedback routes for researchers and their line managers to build trust and understanding within the researcher community, and ensure policy understanding and uptake is high. | 1. New 2. New 3. and 4. Carried over | Feb 2025 June 2027 June 2027 June 2027 | RKED / Comms RKED/HR RKED / Deans & Deputy Deans (RKE) HR | 1. Research Culture Manager (RCM) and internal communications team links enhanced 2. Quarterly meetings with Director of RKED and Director of People, with feedback and actions disseminated to teams as appropriate. 3. Demonstration of regular communication routes between RKED and Deans, monitored regularly by RCM 4. Pulse survey with researchers to gauge level of trust and understanding within the community showing a sustained increase in the measure (benchmark to be collected in first year with target for future year set)
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | 1. Develop new Researcher surveys (CEDARS and/or others) to build awareness of understanding and cultural change. 2. Benchmark data (March - June 2025) and analyse responses in a way that meaningfully captures the views and experiences of research-only staff (particularly those on fixed-term contracts) 3. Engage with individuals at multiple levels through workshops (6 workshops in total; 3 each year with ECRs, Mid-Careers and Profs) to collect qualitative feedback on policies and practices to inform organisational practices 4. Build evaluation approaches (including Pulse surveys and focus groups) to help understand the impact of changes and interventions as part of the researcher development programme, reporting results and action plans regularly to Research Culture Committee. | 1. New 2. New 3. New 4. New | June 2025 December 2025 June 2027 June 2027 | RKED RKED RKED RKED | 1. Implementation of researcher survey as business as usual, with 1st year data used as benchmark to enable understanding of progress reporting throughout the period 2. Target response rate 25% of research staff overall and 15% of research-only staff 3. Feedback after the sessions shows at least 50% of respondents feel RKED are listening to their feedback 4. Action plan demonstrating how feedback has led to change and improvement
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | 1. RKED to hold 6 Research Community events across disciplines (2 per year) to network, develop collaborations and research environment, including PGR cohorts in invite. 2. Develop multiple routes for accessing support, including holding dedicated sessions for staff who have line management responsibility for researchers, to ensure they have the tools they need. 3. Develop multiple routes for accessing support, tailoring approaches to knowledge sharing, such as Pre-award funding opportunities briefing drop-in sessions, to ensure fixed term research staff are included and supported. 4. Continue to develop mentoring framework with the aim of increasing participation, including a requirement that senior academic staff (Profs and Readers) act as mentors to fixed term and early career researchers. | 1. Carried over 2. New 3. New 4. Carried over | June 2027 June 2027 June 2027 June 2026 | RKED RKED RKED RKED/Deans | 1.1 Qualitative researcher feedback after the event indicates a positive effect on research culture and collaboration 1.2 PRES data shows (60% or above) PGRs have a sense of belonging at my institution 2. Qualitative researcher feedback loop during sessions indicate a positive effect on research management 3.1 Recording attendance average across the year (monthly sessions held) 3.2 Researcher Survey shows that researchers feel recognised for their contribution 4. Increased mentee participation in mentoring programme of 10%, building on feedback from the initial year (23/24). | 1.2 PRES SOAS data 2024 shows 50% agree with this statement 4. 2023/2024 figures: 49 mentees and 37 mentors (some mentors took on 2 mentees)
Mental Health and Wellbeing
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | 1. Introduce new routes to understanding the needs of staff and cascade information by appointing department wellbeing ambassadors 2. Actively work with the Workload Allocation Management system (WAMS) development project team to ensure views of all researchers are engaged in the process 3. Encourage line managers of ECRs to include wellbeing in Staff Development Reviews 4. Provide Mental health first aider training for wellbeing ambassadors, building capacity within SOAS to offer guidance on mental health and wellbeing support | 1. New 2. Carried over 3. New 4. New | Dec 2025 June 2026 June 2026 June 2027 | HR/Wellbeing Officer Research Line Managers HR/Wellbeing Officer HR/Wellbeing Officer | 1. Appointment of Wellbeing officers within at least 60% of departments, with plans for complete coverage 2-4. See an improvement in SOAS all staff survey on line management and collection of qualitative feedback. | 2/3. In 2022 staff survey 75% of respondents said their line manager treats them fairly
ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | 1. Develop briefing sessions on effective SDRs with a focus on wellbeing and careers, with specific focus on managers of researchers 2. Ensure all managers are aware of Employee Assistance Programme (EAP) and other routes for support through dedicated briefing sessions for managers | 1. New 2. Carried over | June 2025 June 2025 | HR/Wellbeing Officer HR/Wellbeing Officer | 1 - 2. See a clear improvement (aiming for at least 40%) in staff feeling that their wellbeing is supported in SOAS all staff survey, through CEDAR survey (benchmarking responses in the first year), and collection of qualitative feedback.
ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health. | 1. Encourage line managers to consistently discuss wellbeing with their direct reports, particularly those who are ECRs and post-docs (fixed term) 2. Develop the Personal Research Plan (PRP) template to include a section on wellbeing for line managers of researchers to include in annual review 3. Support line managers in how to model appropriate values and behaviours that create and support a healthy work environment, through management training and clear articulation of management responsibilities. | 1. New 2. New 3. New | June 2025 Sep 2024 Sep 2025 | HoDs/RKE Convenors DVC-RKE/Head of Governance HR | 1 - 3. See a clear improvement (aiming for at least 40%) in staff feeling that their wellbeing is supported in SOAS all staff survey, through CEDAR survey (benchmarking responses in the first year), and collection of qualitative feedback. | 1. In 2022 staff survey 31% of academic staff said they were able to achieve a healthy work/life balance (compared to 59% of professional services)
ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | 1.Requests for flexibility working arrangements to be reviewed by line manager with HR support | 1. New | Dec 2025 | HR | 1. See a high proportion of staff Research staff (75%) believe they are treated fairly in relation to flexible working arrangements through CEDAR survey and collection of qualitative feedback.
ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health. | 1. Continued promotion of Employee Assistance Programme (EAP) offering | 1. Carried over | June 2025 | HR/Wellbeing lead | 1. High level of interaction with online support offering demonstrated though page analytics of relevant intranet pages (benchmarked and future target set in the first year) | 1. New intranet launches Dec 2024
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | 1. Disseminate new disciplinary and grievance policies (agreed in June 2024) with briefings for managers of researchers and research enabling staff from HRBPs 2. Develop new briefings led by HR business partner for academic services to support managers and those raising issues 3. Promote the support areas within the Employee Assistance Programme for staff who report issues 4. Integrate the promotion of the SOAS report and support portal for the reporting and addressing of incidents of discrimination, bullying and harassment into existing programmes. | 1. New 2. New 3. Carried over 4. New | June 2025 Feb 2025 Aug 2025 Sept 2025 | Director of People / HR business partners HR/Research Line Managers HR/Research Line Managers/RKED | 1. See an improvement in SOAS all staff survey on confidence in management 2-3. Researcher Survey shows levels of confidence in reporting bullying and harassment, aiming for above the average 27% in CEDARs report 2023. 4. Increased use of the report and support portal | 1. In 2022 staff survey 27% of staff said they had confidence in senior management 2. Sector benchmarked CEDARS data is at 27% for this question (2023 report).
ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment. | 1. Roll out and encourage attendance of Active Bystander Training for all staff 2. Refresher training for all managers to ensure accurate and up to date understanding of all policies and processes related to discrimination, bullying and harassment in the institution. | 1. New 2. New | June 2027 June 2027 | HR | 1 & 2. Same as P2 EC13
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying. | 1. Review and refresh online tools such as SOAS Report and Support to ensure up to date information is available and response times are in line with expectations. 2. Include section on discrimination, harassment, and bullying in the Research Grant Management Induction pack, signposting to relevant contacts and reporting procedures. 3. Ensure all Professional Services staff with research support remit have key information to signpost to resources and support for discrimination, harassment, bullying, and research misconduct reporting mechanisms. | 1. New 2. New 3. New | June 2026 June 2025 June 2026 | HR RKED RKED | 1- 3. See an improvement (over 40%) in SOAS all staff survey on satisfaction with how bullying / harassment is managed by the institution | 1. In 2022 staff survey 33% of staff said they were satisfied with how bullying / harassment was managed
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | 1. Run six (one per term) Inductions to EDI Processes sessions for managing staff for all line managers with recruitment responsibilities 2. Include information on Equality, Diversity and Inclusion (EDI) in relevant Research staff training 3. Develop multiple routes for raising awareness of offering, and include EDI at all staff meetings (termly) | 1. New 2. New 3. New | June 2026 June 2025 Dec 2024 | HR business partner RKED Deans / DVC-RKE | 1. RCM gather qualitative and quantitative feedback on the sessions 2-3. Researcher Survey / SOAS Staff survey shows that the majority of participants (at least 60%) respond that they believe their institution is committed to EDI
ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | 1. Encourage all researchers to undertake EDI training within their 10 days allowance of professional development 2. Monitor feedback and complaints related to behaviour and practices concerning equality, diversity, and inclusion. | 1. New 2. New | June 2027 June 2027 | RKED/HoDs HR/DVC-RKE | 1. Same as EC14/ECM1 2. At least annual reporting to Research Culture Committee, see a reduction in number of complaints year-on-year
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity, and are able to report infringements or misconduct.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | 1. Develop Researcher Development Programme offer to include sessions on research integrity and professional conduct 2. Timely and transparent communications by Research Integrity Officer of policies and practices, dissemination through the College structures 3. Continue to promote Epigeum Research Integrity course through Dept briefings and all staff newsletter 4. Ensure all Professional Services staff with research support remit are trained on principles of research integrity and ethics, and that they are aware of how to signpost and initiate research misconduct reporting processes. | 1. New 2. New 3. Carried over 4. New | June 2027 June 2025 Aug 2025 Aug 2025 | RKED RKED RKED/HoDs RKED | 1.1 Annual qualitative data gathered as part of training sessions 1.2 Regular engagement of the Research Integrity Officer with colleges and clear links between Researcher Hub and Moodle pages. 2. Same as P1.2 EC15/ECM2 3. Qualitive data gathered as part of feedback from Epigeum 4. 100% staff trained within RKE-D | 1.2 Industry benchmarked CEDARS data is at 54% for research staff and 39% for other academic staff, regarding this question (2023 report).
ECM3 | Ensure managers report and address incidents of poor research integrity. | 1. Develop multiple routes for accessing support by appointing department Research Ethics representatives 2. Continue Research Ethics Panel to report and review cases of poor research integrity, and continue termly Research Ethics bulletin | 1. New 2. Carried over | Dec 2024 June 2026 | HoDs RKED, Deputy Dean for Research Ethics | 1. Same as P1.2 EC15/ECM2 2. Annual report of poor research integrity cases at Research Culture Committee
ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity. | 1. Research Integrity Officer to regularly keep in touch with key staff members to disseminate updates on funder/sector policies | 1. Carried over | 2027-06-01 | RKED | 1. Same as P1.2 EC15/ECM2
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | 1. Continue to promote awareness of Report and Support as an accessible and responsive reporting procedure for all staff 2. Ensure all Professional Services staff with research support remit have key information to signpost to resources and support for recognising and reporting research misconduct. | 3. New | Dec 2024 Aug 2025 | HR RKED | 1. Same as P1.2 EC15/ECM2
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | 1. Continue to actively include ECR and PGR representatives in relevant committees (Senate, Research Committee, College Committees) 2. Actively encourage peer-to-peer support through ECR networks inside and beyond SOAS (such as British Academy London ECR hub) 3. Encourage SOAS leadership teams to actively engage with and consult the ECR network in the development of policies and projects that affect researchers. 4. Develop routes for researchers to work with Professional Services at SOAS | 1. Carried over 2.New 3. New 4. New | Sep 2027 Dec 2024 July 2026 July 2025 | RKED/PVC-RKE RKED DVC-RKE RKED/ PSLT | 1. Committee membership recorded within Committee Terms of Reference (signed off by EB) 2. Increase Research Culture Manager membership and engagement with national ECR networks 3 & 4. Creation of Steering Group between HR, RKED and Researcher Representatives (ECRs, Mid-careers, Profs)
ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | 1. Continue to develop routes to engage with senior management by establishing Research Culture and Environment as a regular agenda item at Senior Management Team (SMT) meetings | 1. New | June 2027 | DVC-RKE | 1. Research Environment and Culture reports received at regular SMT meetings.
EM5 | Engage with opportunities to contribute to relevant policy development within their institution. | 1. As EI7 1 2. Create routes to share and interact with institutional planning and priority setting | 1. Carried over 2. New | Dec 2024 June 2027 | RKED/PVC RKED/PVC | 1. As EI7 1 2. As ECR5
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | As EI7 2, 3 & 4 |  | June 2027 | RKED/ Research SMT / PSLT | 1. Creation of Steering Group between HR, RKED and Researcher Representatives (ECRs, Mid-careers, Profs)
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community. | 1. As EI7 1 and 4 | 1. New | June 2027 | Researchers | 1. Researcher engagement with institutional committees and initiatives, measured through committee membership and anon feedback gathered by RCM from committee membership
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation.
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | 1. Continued use of the Higher Education Role Analysis (HERA) scheme for fair and transparent recruitment. All roles to be reviewed by HR Recruitment Panel (meeting monthly as required). 2. Continue to train all new line managers in 'Recruitment and Selection' to ensure fair and inclusive selection practices for researcher recruitment. 3. Increase awareness of responsible research assessment approaches, and our obligations as a DORA signatory | 1. Carried over 2. Carried over 3. Carried over | Sep 2024 June 2025 June 2026 | HR HR HR/RKED | 1. Standardised working practices related to recruitment 2. All Academic Heads of Department and Researcher Managers to have participated in Recruitment & Selection training before they participate in the hiring process confirmed through training records. 3. Commitment to DORA available on intranet and external website
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | 1a. As part of the induction process for new researchers, pilot the inclusion of a RKED section focusing on key contacts and points of support for research development and delivery. 1b. Enhance the current induction pack for researchers with links to key policies, contacts and support materials, and build into central resource area on researcher development site. 2. Ensure HoDs and researcher managers provide robust and consistent local induction into the Department and College. | 1. New 2. New | Feb 2025 Feb 2027 | RKED Research Line Managers / HoDs | 1. Post-event qualitative feedback form indicates researchers find the event to have been useful, informative, and engaging. 2. Same as above
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | 1. Ensure line managers of researchers promote reward and recognition opportunities available at SOAS, equipping staff at all career stages with a clear understanding of what is required of them and how to approach development. 2. Engage with researchers from protected characteristics groups to work to identify any barriers to promotion processes and build support mechanisms to overcome barriers specific to a range of cohorts. | 1. Carried over 2. New | June 2025 June 2026 | HR/Deans/HoDs/Researchers' Line Managers | 1. Gather insight from researchers on confidence in academic promotions processes at SOAS, demonstrated in staff survey results (benchmarked and future target set in the first year). 2. Qualitative feedback gathered as part of workshops, held at least annually | 1. Sector benchmarked CEDARs data shows 27% of researchers felt the processes at their organisation was clear (2023 report).
EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers. | 1. Encourage line managers of researchers to discuss reward and recognition opportunities as part of SDR 2. Conduct annual equality reviews and consult with Deans to ensure pro-active support for staff seeking academic promotions, including focused support for groups of staff identified as being underrepresented through promotions processes. 3. Ensure consistent and inclusive briefing sessions and clear guidance documents are shared with all researchers and demonstrate equitable and transparent processes in relation to academic promotions. | 1. New 2. New 3. New | June 2025 June 2027 June 2027 | HR/Deans/HoD/Research Line Managers RKED/Deans HR/Deans/HoDs/Research Line Managers | As EI3 1-2
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities.
EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding. | 1a. Equip research support staff with resources and knowledge to highlight codes of practice, relevant policies, and funder terms and conditions at new research grant startup meetings with line managers. 1b. Build on collaborative working approaches between research development and delivery teams and research grant holders to help researchers familiarise themselves with and understand how they need to comply with internal and external expectations and regulations throughout their grant project's lifecycle. 2. Ensure key policies, procedures and legislation are available to researchers, with clear expectations with regards to their role, are available in central resource area on researcher development site. | 1. New 2. New | June 2025 Feb 2025 | RKED/Research Line Managers | 1. Improved collaboration and engagement between research grant holders and research support staff as evident through qualitative feedback in free text responses for initiatives to improve the research environment. 2. Expanded online resources available to researchers. Engagement with resources to be benchmarked and monitored through site analytics
ER1 | Researchers ensure that they work in accordance with institutional policies, procedures and employment legislation, as well as the requirements of their funder. | 1. Employee relations cases for researchers will be tracked and reported on termly as part of the regular reporting for all cases. 2. Researchers actively engage with key policies, procedures and legislation in order to build clear expectations with regards to their role. | 1. Carried over 2. New | June 2025 | Researchers | 1. Implementation of new data collection process with clear reported to the correct channels from 24/25 onwards. 2. High completion rates across all mandatory training
ER2 | Researchers understand their reporting obligations and responsibilities. | As ER1 | 1. New | June 2025 | Researchers
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | 1. Provide a range of development opportunities, both internal and external, to support development of research leadership skills. | 1. New | June 2027 | RKED | 1. Researcher Development Hub programme to include a breadth of internal/external opportunities
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | 1. Support Deans and HoDs in the fair and transparent implementation of WAMS (workload allocation management system) in order to support research-only staff in their development in preparation for reward and promotion processes 2. Champion and celebrate excellent people management through staff communication 3. Build repository of resources and training through Researcher Development Programme to demonstrate approaches to, and examples of, excellent people management | 1. New 2. New 3. New | June 2025 June 2026 June 2027 | HR/Deans/HoDs/Research Line Managers Senior Management team/Deputy Deans/HR RKED | 1. As EI3 1. 2. As EI7 1 3. Expanded online resources available to researchers. Engagement with resources to be benchmarked and monitored through site analytics | 1. Sector benchmarked CEDARS data shows 27% of researchers agree to this question (2023 report).
EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care. | 1. Include within Researcher Development Hub intranet site examples of 'good practice' for managers to access and adopt as needed to support their own practice | 1. New | 2025-02-01 | RKED | 1. Researcher Survey to indicate level at which managers of researchers feel valued for managing and developing researchers. Benchmark in the first year, with the aim to improve outcome in the second survey | 1. Sector benchmarked CEDARs data shows 44% of managers of researchers don't feel valued for managing staff performance (2023 report).
EM4 | Managers actively engage in regular constructive performance management with their researchers. | 1. Build consistency across all Colleges to ensure line managers of researchers regularly meet with their reports to develop their research plans and identify development opportunities, | 1. New | Sep 2026 | Research Line Managers | 1. The high level of engagement with PRP process (Over 80% of research staff have completed a PRP in 23/24),is consistently met across all colleges
ER3 | Researchers positively engage with performance management discussions and reviews with their managers. | 1. Researchers actively engage with SDR processes | 1. New | July 2026 | Researchers | 1. Specific areas of low uptake are identified and action plans in place to address. Aim for 80% uptake overall. | 1. 70% of research/academic staff completed their SDR in 2023
Job security
The aim of this obligation is to improve the job security of researchers.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | 1. Engage with researchers on temporary contracts to identify funding and grants 2a. Ensure 2-year FTC minimum contracts (where funding permits) are offered as standard and clearly stipulated in the advertising process. 2b. Ensure all researchers with 4 years or more continuous service are able to move to open-ended contracts 3. Create and monitor adherence to ending of FTC procedure. | 1. New 2. New 3. New | June 2026 Dec 2024 June 2027 | RKED / Research Line Managers HR HR | 1. Record attendance at Pre-award development drop-in sessions held monthly 2 & 3. Annual report at Research Culture Committee
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it.
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | 1. Build resources within Researcher Development Hub intranet site to signpost to key internal and external training from a range of providers to support a range of career paths 2. Create routes for communication by developing regular newsletters with opportunities for the career stages highlighting the range of activities which could be undertaken as part of the allocations (e.g. not just training, but mentoring, shadowing, coaching etc) | 1. New 2. New | June 2025 June 2025 | RKED RKED / Careers / HR | 1 & 2. High level of interaction with online support offering demonstrated though page analytics of relevant intranet pages (benchmarked in the first year)
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | 1. Develop effective monitoring and reporting of attendance across the range of professional development initiatives and training | 1. New | June 2026 | HR / RKED / Careers | 1. Report attendance and qualitative data as part of programme at Research Culture Committee annually, with demonstrable use of findings to develop the programme in following years
PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development. | As PCDI 1-2
PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year. | As ER3
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers. | 1. Provide tailored training on Staff Development Review (SDR) for researchers and line managers of researchers to ensure meaningful career development | 1. New | June 2026 | HR | 1. As ER3
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews. | 1. Develop routes for researchers to feed back on their experience of SDR and career planning discussions to understand needs of researchers, and develop action plan for change where required | 1. New | June 2027 | HR / HoDs | 1. Multiple routes for engagement and feedback developed with regular reporting on action plan
PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually. | 1. Encourage Deans and HoDs to monitor uptake of SDR and research planning meetings with researchers, setting targets for completion rates where low level of uptake. | 1. New | June 2027 | HR/RKED | 1. As ER3
PCDR4 | Researchers positively engage in career development reviews with their managers. | 1. Researchers to engage with the range of career development support activities offered, and work with their managers to understand and develop personal plans for development | 1. New | June 2027 | Researchers | 1. Researchers feel supported to take personal responsibility for their career development through survey and qual feedback routes. Monitor through CEDARs with benchmarking and target setting in first year
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | 1. Increase access to advice on careers paths and relevant external networks through resources and signposting within Researcher Development Hub intranet site 2. Collect and review data on the range of activities undertaken by researchers as part of the 10 day allocation for research development to inform future development of the Researcher Development Programme 3. Further develop internal Research Mentoring Framework, to enable even more cross-College and interdisciplinary career development | 1. New 2. New 3. Carried over | June 2026 June 2026 Dec 2024 | Careers / RKED RKED RKED/HoD | 1. Qualitative data gathered as part of programme 2. Researcher Survey shows that participants that they are aware of institutional support offered and feel supported in their career development aspirations. Target to reach and exceed benchmarked sector average on relevant CEDARs question (55%) 3. As ECR1 3 | 2. Sector benchmarked CEDARS data shows 55% of researchers agree to this question (2023 report).
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications. | 1. Enable effective monitoring of engagement in Staff Development Review (SDR) between researchers and researcher managers, and regular training report updates to key stakeholders | 1. New | June 2027 | Deans/HoDs/Line Managers | 1. Reporting route from Colleges annually to the Research Culture Committee established
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | 1. Encourage researchers to make use of tools such as the Research Information System to curate and promote their researcher profiles internally and externally 2. Ensure training and resources with a focus on leadership and personal effectiveness are developed and included within Researcher Development Hub intranet site and Research Development Programme 3. Increase researcher engagement in external, cohort specific programmes such as Aurora | 1. New 2. New 3. New | June 2027 June 2026 | RKED / HoDs / Research Line Managers RKED | 1. Roll out of new Worktribe profiles module with engagement events for staff to encourage uptake. 2. Development and roll out of online content, monitored through site analytics 3. Monitor number of staff accepted onto external leadership programmes, and set future targets
PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours. | As PCDI 1-2
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development. | As EM1
PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills | 1. Researchers actively apply for funding to develop and deliver new researcher development initiatives through the internal research culture fund | 1. New | June 2027 | Researchers | 1. Increased number of staff funded through the research culture funding schemes by 20% (from 15 awards to 18)
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | 1. Increase awareness of pathways for Knowledge Transfer Partnerships (KTP) with industry by creating resources in the Researcher Development Hub intranet site and ensure signposting to researcher jobs in roles that straddle academia and industry 2. Feedback development needs, barriers, and incongruencies facing practice researchers to researcher development and research environment/culture industry leaders and funders. | 1. New 2. New | Feb 2025 June 2027 | RKED / Careers RKED / Careers | 1. Roll out of site content and collection of site analytics to demonstrate coverage. 2. Generate report as part of feedback loops (workshops, focus groups etc) to be reported at least annually at Research Culture Committee
PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments. | 1. Provide regular updates and briefings for managers of researchers on career development, pathways and opportunities to enable them to support researchers in gaining experience. | 1. New | June 2027 | RKED / Careers | 1. Qualitative feedback gathered as part of regular reporting between Colleges and Deputy Dean Research Culture and RCM
PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments. | 1. Ensure mentorship and development support offered through Research Development Programme and other routes includes a recognition of the range of researcher careers and sectors. | 1. New | June 2025 | RKED | 1. Utilise feedback and interactions with attendees of the RDP
PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation. | 1. Develop Public Policy and Engagement resources within Research Development Hub intranet site 2. Increase awareness of research enterprise activities and utilise SOAS' unique areas of research by developing news stories (blogs etc) of activities | 1. New 2. New | June 2027 June 2025 | RKED RKED | 1 & 2. Roll out of site content and collection of site analytics to demonstrate coverage.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | https://www.soas.ac.uk/research/research-and-knowledge-exchange/hr-excellence-research-award |  |  |  | RKED | Research and Knowledge Exchange Directorate
2 | https://www.soas.ac.uk/sites/default/files/2022-08/Research-and-Knowledge-Exchange-Strategy-2021-26.pdf |  |  |  | HoD | Head of Department
3 | https://www.soas.ac.uk/sites/default/files/2022-07/Equality%2C-Diversity-and-Inclusion-Strategy-2021-25.pdf |  |  |  | DVC-RKED | Deputy Vice Chancellor - Research and Knowledge Exchange
4 |  |  |  |  | RCC | Research Culture Committee
5 |  |  |  |  | SMT | Senior Management Team
6 |  |  |  |  | FTC | Fixed term contract
7 |  |  |  |  | PSLT | Professional Services Leadership team
8 |  |  |  |  | Research SMT | Research Senior Management team
9 |  |  |  |  | SDR | Staff Development Review
10 |  |  |  |  | PRP | Personal Research Plan
11 |  |  |  |  | WAMS | Workload Allocation Management System
12
13
14
15
16
17
18
19
20

## Funders' obligations (hidden)
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions
Employment
Job security
The aims of these obligation are to improve the job security of early career researchers.
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to do so.
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Guidance (hidden)
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: | Enter relevant information |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | Enter relevant information |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | Enter relevant information |  |  |  | Research staff |  |  | These are your primary beneficiaries, and should be prioritised across the action plan - both by being targeted with actions and evaluated through success measures.
| Institutional context: | Enter relevant information that helps frame the action plan and the intended institutional audience. For example, this box can be used to disclose the research intensiveness of the institution, providing a justification for the breadth/depth of the actions disclosed. |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Describe here your actions/interventions for meeting the obligation, referring to actions elsewhere in the action plan if preferred. | Has the action been carried forward from a previous action plan? "yes" / "no" | Indicate a month and year | Name all key parties responsible for the action(s) and success measure(s) | Describe here your success measure(s), used to report against the intended impact for researchers and incorporating researchers' views wherever possible. | Describe here any supplementary information. | Describe here a written summary of the progress made against the obligation, taking a broad view of the people and/or organisational development that may have occurred. | Provide evidence that directly reports against all success measures described previously. | Indicate the next steps for the action from the following options: "ongoing" (if the deadline is scheduled in the future), "carried forward" (if the action was not completed as planned by the initial deadline) or "no further action" (accompanied by a brief explanation).
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | Institutions planning actions for specific funders' obligations can insert these obligations into the relevant section of the institution template.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | Use these spaces to provide links and references for information provided in the action plan. |  |  |  |  | Use these spaces to describe abbreviations and
2 | [5 empty] | terms used in the action plan.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
N.B. This section is for reporting only, and should not be completed prior to the beginning of the action plan's term.
For brevity, the remaining obligations have been omitted from this 'Guidance' sheet.

## Tips (hidden)
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff |  |  | Only include institutional audiences considered to directly benefit from the action plan, remembering that research staff should be prioritised.
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers. Our internal evaluation revealed that researchers feel the university strategic priorities do not reflect their own (62% in a consultation said that they felt disconnected from the university's recent 'Strategy 2030'). Heads of Faculties also report from conversations at committee meetings that researchers feel the university's strategic priorities are not entirely aligned with the reality felt in specific research disciplines. Optional: Institutions can use this space (if desired) to discuss the context that frames the actions and success measures disclosed.
ECI1 | Ensure all relevant staff are aware of the Concordat
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | Providing actions for every obligation is not mandatory, although action plans should aim to target those in their priority areas and/or those highlighted by researchers during the internal evaluation.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Host programme of Faculty- and institution-wide workshops on research culture, capturing local and broader views on key themes in research and reflecting these with the institution's 'Strategy 2030' priorities. Gather a comprehensive range of anonymous views from research staff on how they feel their Faculty research environment compares to the institution as a whole through quarterly Faculty pulse surveys. | no yes | Jul-23 Being specific (rather than only stating "ongoing" or "annually") indicates that reporting has been properly scheduled and that actions are timebound. May-23 | • RCWG • Heads of Faculties • PVC-RI • Faculty-HR • RCWG Broad and specific responsibility can show a joined-up approach to working, connects institutional stakeholders around the Researcher Development Concordat and also shares the workload. | • Host quarterly workshops for each Faculty, and biannual institutional workshops. Success measures like this (i.e., "action completed") are acceptable but should be complemented by other measures that show the impact of the action. • Drafting of workshop reports led by research staff attendees, and reports instated as a standing agenda item at Faculty committee meetings. • At least 30 research staff attendance (on average) at Faculty workshops. Positive post-event feedback from at least 80% of research staff attendees. • At least 40% of research staff (on average) across all 5 Faculties respond to Faculty pulse surveys. Success measures like these allow institutions to qualitatively and quantitatively assess progress against the obligation. Note the words underlined in the obligation and consider how the success measures could align with these. Setting numerical (i.e., SMART) targets can provide an unambiguous benchmark to report progress against in the future. |  | Programme of workshops conducted digitally due to ongoing COVID restrictions (1). Attendance was encouraging, with a good number of research staff joining and contributing to both discussions and the chat function. Research staff were less engaged in the reporting of the workshops than hoped, partially attributed to the less stimulating setting of online events. Feedback from research staff attendees was very positive, and both this feedback and the workshop discussion points were fed into Faculty committee meetings. In one instance, this prompted a Head of Faculty to set up focus groups to explore one particular issue more closely. Faculty pulse survey engagement was encouraging, albeit variable across the Faculties. The findings and trends will help inform future Concordat action plans and the university's Research Culture manifesto. By describing the action's progress in narrative form, institutions can explain success in greater detail, or mitigate challenges experienced, by providing helpful contextual information. | • All 5 Faculties' workshops held quarterly, as well as two workshops held at an institutional level. • Workshop reporting only partially led by research staff across the Faculties. All Faculty committees successfully instated research culture reports as an agenda item. • 34 research staff attended each workshop on average. 86% of research staff attendees gave positive post-event feedback, with 84% saying they "found the workshop to be helpful". • 38±3% of research staff responded to pulse surveys across all Faculties, although some only received 35% research staff response rates. Ensuring you report against all success measures provides a better assessment of the impact achieved and shows commitment to researchers that the institution cares about their views and behaviour. | no further action (action now considered normal business) After selecting from one of the set responses in the column header, institutions can briefly indicate the rationale for this decision (e.g., "action successfully embedded" or "action delayed, partially completed").
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Even if no action is intended/needed, it is encouraged to include success measures that show how different stakeholders engage with/benefit from other actions. |  | Jul-23 | • RCWG | At least 70% of research staff answering CEDARS q42.4 ("feel included in your immediate research environment/group") agree or strongly agree (CEDARS 2021: 62%) | Survey response rate in 2021: 16% research staff (n=147) Optional: This space can be used to provide details not suitable for the other columns. For example, you can add information relevant to an action and/or a success measure to help demonstrate feasibility. | CEDARS response rate improved considerably after a campaign of targeted communications. This coincided with less positive responses for q42.4 than anticipated, suggesting that the university is now successfully reaching a previously 'silent' yet dissatisfied group of research staff with the survey. | 64% of research staff responded agree/strongly agree for CEDARS q42.4. 22% of all research staff (n=202) responded to CEDARS.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and Supplementary Information (more rows can be added) |  |  |  |  | Abbreviations and Glossary (more rows can be added)
1 | www.university.ac.uk/researchculture/researchcultureworkshops/summary |  |  |  | PVC-RI | Pro-Vice Chancellor for Research & Innovation
2 | Using these spaces can help keep the main body of the action plan as concise as possible. |  |  |  | RCWG | Research Culture Working Group
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
This sheet gives a hypothetical response to a group of obligations under Environment and Culture > Awareness and engagement.
Tips and advice are shown alongside to highlight how to organise actions and success measures to deliver the most impact, as well as to demonstrate a transparent and compelling approach to reporting on progress and the original success measure.
For brevity, the remaining obligations have been omitted from this 'Tips' sheet.